## Document_Detail
scraped_at | cluster_code | clean_list_name | work_order_number | route | scope | phase | route_summary_status | astri_type | astri_label | derived_status | file_count | upload_date | verified_by | verified_at | revision_by | revision_at | revision_remark | filename | detail_url
2026-08-19 17:31 | TRG000038 | LOA IPUH RT 71 SAMPAI 75 KUTAI KARTANEGARA | WO/KUTAI KARTANEGARA/2026/INST/10/8313 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | - | as_plan_drawing_dwg | APD DWG Cluster | APPROVED | 1 | 2026-08-06 12:35 | moch.putro |  |  |  |  | as_plan_drawing_dwg_TRG000038_20260806123512_TRG000038 APD DWG LOA IPUH RT 71 SAMPAI 75 KUTAI KARTANEGARA.dwg | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=TRG000038&work_order_number=WO%2FKUTAI%20KARTANEGARA%2F2026%2FINST%2F10%2F8313&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:31 | TRG000038 | LOA IPUH RT 71 SAMPAI 75 KUTAI KARTANEGARA | WO/KUTAI KARTANEGARA/2026/INST/10/8313 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | - | as_plan_drawing_kmz | APD KMZ Cluster | APPROVED | 2 | 2026-08-06 12:52 | moch.putro |  |  |  |  | as_plan_drawing_kmz_TRG000038_20260806125200_TRG000038 APD KMZ LOA IPUH RT 71 SAMPAI 75 KUTAI KARTANEGARA.kmz | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=TRG000038&work_order_number=WO%2FKUTAI%20KARTANEGARA%2F2026%2FINST%2F10%2F8313&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:31 | TRG000038 | LOA IPUH RT 71 SAMPAI 75 KUTAI KARTANEGARA | WO/KUTAI KARTANEGARA/2026/INST/10/8313 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | - | as_plan_drawing_subfeeder_kmz | APD Subfeeder kmz | ON REVIEW | 2 | 2026-08-06 12:38 | [5 empty] | as_plan_drawing_subfeeder_kmz_TRG000038_20260806123810_TRG000038 APD KMZ SUBFEEDER LOA IPUH RT 71 SAMPAI 75 KUTAI KARTANEGARA.kmz | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=TRG000038&work_order_number=WO%2FKUTAI%20KARTANEGARA%2F2026%2FINST%2F10%2F8313&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:31 | TRG000038 | LOA IPUH RT 71 SAMPAI 75 KUTAI KARTANEGARA | WO/KUTAI KARTANEGARA/2026/INST/10/8313 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | - | permit_subfeeder | BA Permit Subfeeder | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=TRG000038&work_order_number=WO%2FKUTAI%20KARTANEGARA%2F2026%2FINST%2F10%2F8313&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:31 | TRG000038 | LOA IPUH RT 71 SAMPAI 75 KUTAI KARTANEGARA | WO/KUTAI KARTANEGARA/2026/INST/10/8313 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | - | permit_cluster_aggreement | Berita Acara Kesepakatan | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=TRG000038&work_order_number=WO%2FKUTAI%20KARTANEGARA%2F2026%2FINST%2F10%2F8313&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:31 | TRG000038 | LOA IPUH RT 71 SAMPAI 75 KUTAI KARTANEGARA | WO/KUTAI KARTANEGARA/2026/INST/10/8313 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | - | permit_open | Berita Acara Open | ON REVIEW | 1 | 2026-07-23 21:33 | [5 empty] | permit_open_TRG000038_20260723213322_BA OPEN LOA IPUH RT 71 SAMPAI 75 KUTAI KARTANEGARA.pdf | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=TRG000038&work_order_number=WO%2FKUTAI%20KARTANEGARA%2F2026%2FINST%2F10%2F8313&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:31 | TRG000038 | LOA IPUH RT 71 SAMPAI 75 KUTAI KARTANEGARA | WO/KUTAI KARTANEGARA/2026/INST/10/8313 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | - | donation_approval | Cluster Approval Proposal | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=TRG000038&work_order_number=WO%2FKUTAI%20KARTANEGARA%2F2026%2FINST%2F10%2F8313&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:31 | TRG000038 | LOA IPUH RT 71 SAMPAI 75 KUTAI KARTANEGARA | WO/KUTAI KARTANEGARA/2026/INST/10/8313 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | - | civil_work_acceptance_test | CW ATP | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=TRG000038&work_order_number=WO%2FKUTAI%20KARTANEGARA%2F2026%2FINST%2F10%2F8313&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:31 | TRG000038 | LOA IPUH RT 71 SAMPAI 75 KUTAI KARTANEGARA | WO/KUTAI KARTANEGARA/2026/INST/10/8313 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | - | subfeeder_civil_work_acceptance_test | CW ATP Subfeeder | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=TRG000038&work_order_number=WO%2FKUTAI%20KARTANEGARA%2F2026%2FINST%2F10%2F8313&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:31 | TRG000038 | LOA IPUH RT 71 SAMPAI 75 KUTAI KARTANEGARA | WO/KUTAI KARTANEGARA/2026/INST/10/8313 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | - | cluster_survey_form | Form Cluster Survey | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=TRG000038&work_order_number=WO%2FKUTAI%20KARTANEGARA%2F2026%2FINST%2F10%2F8313&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:31 | TRG000038 | LOA IPUH RT 71 SAMPAI 75 KUTAI KARTANEGARA | WO/KUTAI KARTANEGARA/2026/INST/10/8313 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | - | permit_vip_form | Form Free Layanan | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=TRG000038&work_order_number=WO%2FKUTAI%20KARTANEGARA%2F2026%2FINST%2F10%2F8313&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:31 | TRG000038 | LOA IPUH RT 71 SAMPAI 75 KUTAI KARTANEGARA | WO/KUTAI KARTANEGARA/2026/INST/10/8313 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | - | homepass_database | Homepass Database | APPROVED | 1 | 2026-08-06 12:35 | moch.putro |  |  |  |  | homepass_database_TRG000038_20260806123511_TRG000038 APD HPDB LOA IPUH RT 71 SAMPAI 75 KUTAI KARTANEGARA.xlsx | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=TRG000038&work_order_number=WO%2FKUTAI%20KARTANEGARA%2F2026%2FINST%2F10%2F8313&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:31 | TRG000038 | LOA IPUH RT 71 SAMPAI 75 KUTAI KARTANEGARA | WO/KUTAI KARTANEGARA/2026/INST/10/8313 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | - | rough_design_layout | Layout SnD Kasar | ON REVIEW | 1 | 2026-07-23 21:33 | [5 empty] | rough_design_layout_TRG000038_20260723213323_LOA IPUH RT 71 SAMPAI 75 KUTAI KARTANEGARA.pdf | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=TRG000038&work_order_number=WO%2FKUTAI%20KARTANEGARA%2F2026%2FINST%2F10%2F8313&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:31 | TRG000038 | LOA IPUH RT 71 SAMPAI 75 KUTAI KARTANEGARA | WO/KUTAI KARTANEGARA/2026/INST/10/8313 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | - | sales_validation_layout | Layout Validasi Sales | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=TRG000038&work_order_number=WO%2FKUTAI%20KARTANEGARA%2F2026%2FINST%2F10%2F8313&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:31 | TRG000038 | LOA IPUH RT 71 SAMPAI 75 KUTAI KARTANEGARA | WO/KUTAI KARTANEGARA/2026/INST/10/8313 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | - | ptsp | PTSP | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=TRG000038&work_order_number=WO%2FKUTAI%20KARTANEGARA%2F2026%2FINST%2F10%2F8313&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:31 | TRG000038 | LOA IPUH RT 71 SAMPAI 75 KUTAI KARTANEGARA | WO/KUTAI KARTANEGARA/2026/INST/10/8313 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | - | redline | Redline | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=TRG000038&work_order_number=WO%2FKUTAI%20KARTANEGARA%2F2026%2FINST%2F10%2F8313&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:31 | TRG000038 | LOA IPUH RT 71 SAMPAI 75 KUTAI KARTANEGARA | WO/KUTAI KARTANEGARA/2026/INST/10/8313 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | - | subfeeder_redline | Redline Subfeeder | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=TRG000038&work_order_number=WO%2FKUTAI%20KARTANEGARA%2F2026%2FINST%2F10%2F8313&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:31 | TRG000038 | LOA IPUH RT 71 SAMPAI 75 KUTAI KARTANEGARA | WO/KUTAI KARTANEGARA/2026/INST/10/8313 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | - | rekomtek | Rekomtek | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=TRG000038&work_order_number=WO%2FKUTAI%20KARTANEGARA%2F2026%2FINST%2F10%2F8313&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:31 | TRG000038 | LOA IPUH RT 71 SAMPAI 75 KUTAI KARTANEGARA | WO/KUTAI KARTANEGARA/2026/INST/10/8313 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | - | tssr | TSSR | APPROVED | 1 | 2026-08-06 12:35 | moch.putro |  |  |  |  | tssr_TRG000038_20260806123513_TSSR LOA IPUH RT 71 SAMPAI 75 KUTAI KARTANEGARA.pdf | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=TRG000038&work_order_number=WO%2FKUTAI%20KARTANEGARA%2F2026%2FINST%2F10%2F8313&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:31 | TRG000038 | LOA IPUH RT 71 SAMPAI 75 KUTAI KARTANEGARA | WO/KUTAI KARTANEGARA/2026/INST/10/8313 | ATP CLUSTER - FULL OPM | CLUSTER | FULL OPM | - | opm_otdr_acceptance_test | OPM / OTDR ATP | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/full-opm?cluster_code=TRG000038&work_order_number=WO%2FKUTAI%20KARTANEGARA%2F2026%2FINST%2F10%2F8313&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:31 | TRG000038 | LOA IPUH RT 71 SAMPAI 75 KUTAI KARTANEGARA | WO/KUTAI KARTANEGARA/2026/INST/10/8313 | ATP CLUSTER - RFS | CLUSTER | RFS | - | build_of_quantity_as_built_drawing | ABD BoQ Cluster | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/rfs?cluster_code=TRG000038&work_order_number=WO%2FKUTAI%20KARTANEGARA%2F2026%2FINST%2F10%2F8313&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:31 | TRG000038 | LOA IPUH RT 71 SAMPAI 75 KUTAI KARTANEGARA | WO/KUTAI KARTANEGARA/2026/INST/10/8313 | ATP CLUSTER - RFS | CLUSTER | RFS | - | as_built_drawing_dwg | ABD Cluster DWG | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/rfs?cluster_code=TRG000038&work_order_number=WO%2FKUTAI%20KARTANEGARA%2F2026%2FINST%2F10%2F8313&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:31 | TRG000038 | LOA IPUH RT 71 SAMPAI 75 KUTAI KARTANEGARA | WO/KUTAI KARTANEGARA/2026/INST/10/8313 | ATP CLUSTER - RFS | CLUSTER | RFS | - | as_built_drawing_kmz | ABD Cluster KMZ | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/rfs?cluster_code=TRG000038&work_order_number=WO%2FKUTAI%20KARTANEGARA%2F2026%2FINST%2F10%2F8313&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:31 | TRG000038 | LOA IPUH RT 71 SAMPAI 75 KUTAI KARTANEGARA | WO/KUTAI KARTANEGARA/2026/INST/10/8313 | ATP CLUSTER - RFS | CLUSTER | RFS | - | build_of_quantity_as_plan_drawing | BoQ APD | APPROVED | 1 | 2026-08-06 12:35 | moch.putro |  |  |  |  | build_of_quantity_as_plan_drawing_TRG000038_20260806123513_TRG000035 APD BOQ LOA IPUH RT 71 SAMPAI 75 KUTAI KARTANEGARA.xlsx | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/rfs?cluster_code=TRG000038&work_order_number=WO%2FKUTAI%20KARTANEGARA%2F2026%2FINST%2F10%2F8313&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:31 | TRG000038 | LOA IPUH RT 71 SAMPAI 75 KUTAI KARTANEGARA | WO/KUTAI KARTANEGARA/2026/INST/10/8313 | ATP CLUSTER - RFS | CLUSTER | RFS | - | core_management | Core Management | ON REVIEW | 1 | 2026-08-19 17:14 | [5 empty] | core_management_TRG000038_20260819171423_TRG000038 PRE ABD HPDB LOA IPUH RT 71 SAMPAI 75 KUTAI KARTANEGARA.xlsx | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/rfs?cluster_code=TRG000038&work_order_number=WO%2FKUTAI%20KARTANEGARA%2F2026%2FINST%2F10%2F8313&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:31 | TRG000038 | LOA IPUH RT 71 SAMPAI 75 KUTAI KARTANEGARA | WO/KUTAI KARTANEGARA/2026/INST/10/8313 | ATP CLUSTER - RFS | CLUSTER | RFS | - | justifikasi_berita_acara_opname | Justifikasi Berita Acara Opname | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/rfs?cluster_code=TRG000038&work_order_number=WO%2FKUTAI%20KARTANEGARA%2F2026%2FINST%2F10%2F8313&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:31 | TRG000038 | LOA IPUH RT 71 SAMPAI 75 KUTAI KARTANEGARA | WO/KUTAI KARTANEGARA/2026/INST/10/8313 | ATP CLUSTER - RFS | CLUSTER | RFS | - | project_opname | Project Opname | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/rfs?cluster_code=TRG000038&work_order_number=WO%2FKUTAI%20KARTANEGARA%2F2026%2FINST%2F10%2F8313&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:31 | TRG000038 | LOA IPUH RT 71 SAMPAI 75 KUTAI KARTANEGARA | WO/KUTAI KARTANEGARA/2026/INST/10/8313 | ATP CLUSTER - RFS | CLUSTER | RFS | - | subfeeder_project_opname | Project Opname Subfeeder | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/rfs?cluster_code=TRG000038&work_order_number=WO%2FKUTAI%20KARTANEGARA%2F2026%2FINST%2F10%2F8313&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:31 | TRG000038 | LOA IPUH RT 71 SAMPAI 75 KUTAI KARTANEGARA | WO/KUTAI KARTANEGARA/2026/INST/10/8313 | PROJECT OPNAME - CLUSTER | CLUSTER | PROJECT OPNAME |  | build_of_quantity_as_built_drawing | ABD BoQ Cluster | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/material/cluster/project-opname/review?cluster_code=TRG000038&work_order_number=WO/ALL/2026/DOCU/16/80219&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:31 | TRG000038 | LOA IPUH RT 71 SAMPAI 75 KUTAI KARTANEGARA | WO/KUTAI KARTANEGARA/2026/INST/10/8313 | PROJECT OPNAME - CLUSTER | CLUSTER | PROJECT OPNAME |  | as_built_drawing_dwg | ABD Cluster DWG | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/material/cluster/project-opname/review?cluster_code=TRG000038&work_order_number=WO/ALL/2026/DOCU/16/80219&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:31 | TRG000038 | LOA IPUH RT 71 SAMPAI 75 KUTAI KARTANEGARA | WO/KUTAI KARTANEGARA/2026/INST/10/8313 | PROJECT OPNAME - CLUSTER | CLUSTER | PROJECT OPNAME |  | as_built_drawing_kmz | ABD Cluster KMZ | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/material/cluster/project-opname/review?cluster_code=TRG000038&work_order_number=WO/ALL/2026/DOCU/16/80219&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:31 | TRG000038 | LOA IPUH RT 71 SAMPAI 75 KUTAI KARTANEGARA | WO/KUTAI KARTANEGARA/2026/INST/10/8313 | PROJECT OPNAME - CLUSTER | CLUSTER | PROJECT OPNAME |  | build_of_quantity_as_plan_drawing | BoQ APD | APPROVED | 1 | 2026-08-06 12:35 | moch.putro |  |  |  |  | build_of_quantity_as_plan_drawing_TRG000038_20260806123513_TRG000035 APD BOQ LOA IPUH RT 71 SAMPAI 75 KUTAI KARTANEGARA.xlsx | https://astri.morarepublic.co.id/material/cluster/project-opname/review?cluster_code=TRG000038&work_order_number=WO/ALL/2026/DOCU/16/80219&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:31 | TRG000038 | LOA IPUH RT 71 SAMPAI 75 KUTAI KARTANEGARA | WO/KUTAI KARTANEGARA/2026/INST/10/8313 | PROJECT OPNAME - CLUSTER | CLUSTER | PROJECT OPNAME |  | build_of_quantity_project_opname | BOQ Project Opname | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/material/cluster/project-opname/review?cluster_code=TRG000038&work_order_number=WO/ALL/2026/DOCU/16/80219&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:31 | TRG000038 | LOA IPUH RT 71 SAMPAI 75 KUTAI KARTANEGARA | WO/KUTAI KARTANEGARA/2026/INST/10/8313 | PROJECT OPNAME - CLUSTER | CLUSTER | PROJECT OPNAME |  | justifikasi_berita_acara_opname | Justifikasi Berita Acara Opname | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/material/cluster/project-opname/review?cluster_code=TRG000038&work_order_number=WO/ALL/2026/DOCU/16/80219&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:31 | TRG000038 | LOA IPUH RT 71 SAMPAI 75 KUTAI KARTANEGARA | WO/KUTAI KARTANEGARA/2026/INST/10/8313 | PROJECT OPNAME - CLUSTER | CLUSTER | PROJECT OPNAME |  | opm_otdr_acceptance_test | OPM / OTDR ATP | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/material/cluster/project-opname/review?cluster_code=TRG000038&work_order_number=WO/ALL/2026/DOCU/16/80219&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:31 | TRG000038 | LOA IPUH RT 71 SAMPAI 75 KUTAI KARTANEGARA | WO/KUTAI KARTANEGARA/2026/INST/10/8313 | PROJECT OPNAME - CLUSTER | CLUSTER | PROJECT OPNAME |  | project_opname | Project Opname | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/material/cluster/project-opname/review?cluster_code=TRG000038&work_order_number=WO/ALL/2026/DOCU/16/80219&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:31 | TRG000038 | LOA IPUH RT 71 SAMPAI 75 KUTAI KARTANEGARA | WO/KUTAI KARTANEGARA/2026/INST/10/8313 | ATP SUBFEEDER - CW ATP | SUBFEEDER | CW ATP | - | as_plan_drawing_core_management_subfeeder | APD Core Management Subfeeder | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/subfeeder/list/by-invoice-phase/cw-atp?cluster_code=TRG000038&work_order_number=WO%2FKUTAI%20KARTANEGARA%2F2026%2FINST%2F10%2F8313&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:31 | TRG000038 | LOA IPUH RT 71 SAMPAI 75 KUTAI KARTANEGARA | WO/KUTAI KARTANEGARA/2026/INST/10/8313 | ATP SUBFEEDER - CW ATP | SUBFEEDER | CW ATP | - | as_plan_drawing_subfeeder_dwg | APD Subfeeder dwg | ON REVIEW | 1 | 2026-08-06 12:38 | [5 empty] | as_plan_drawing_subfeeder_dwg_TRG000038_20260806123810_TRG000035 APD DWG SUBFEEDER LOA IPUH RT 71 SAMPAI 75 KUTAI KARTANEGARA.dwg | https://astri.morarepublic.co.id/rfs-document/subfeeder/list/by-invoice-phase/cw-atp?cluster_code=TRG000038&work_order_number=WO%2FKUTAI%20KARTANEGARA%2F2026%2FINST%2F10%2F8313&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:31 | TRG000038 | LOA IPUH RT 71 SAMPAI 75 KUTAI KARTANEGARA | WO/KUTAI KARTANEGARA/2026/INST/10/8313 | ATP SUBFEEDER - CW ATP | SUBFEEDER | CW ATP | - | as_plan_drawing_subfeeder_kmz | APD Subfeeder kmz | ON REVIEW | 2 | 2026-08-06 12:38 | [5 empty] | as_plan_drawing_subfeeder_kmz_TRG000038_20260806123810_TRG000038 APD KMZ SUBFEEDER LOA IPUH RT 71 SAMPAI 75 KUTAI KARTANEGARA.kmz | https://astri.morarepublic.co.id/rfs-document/subfeeder/list/by-invoice-phase/cw-atp?cluster_code=TRG000038&work_order_number=WO%2FKUTAI%20KARTANEGARA%2F2026%2FINST%2F10%2F8313&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:31 | TRG000038 | LOA IPUH RT 71 SAMPAI 75 KUTAI KARTANEGARA | WO/KUTAI KARTANEGARA/2026/INST/10/8313 | ATP SUBFEEDER - CW ATP | SUBFEEDER | CW ATP | - | permit_subfeeder | BA Permit Subfeeder | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/subfeeder/list/by-invoice-phase/cw-atp?cluster_code=TRG000038&work_order_number=WO%2FKUTAI%20KARTANEGARA%2F2026%2FINST%2F10%2F8313&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:31 | TRG000038 | LOA IPUH RT 71 SAMPAI 75 KUTAI KARTANEGARA | WO/KUTAI KARTANEGARA/2026/INST/10/8313 | ATP SUBFEEDER - CW ATP | SUBFEEDER | CW ATP | - | subfeeder_civil_work_acceptance_test | CW ATP Subfeeder | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/subfeeder/list/by-invoice-phase/cw-atp?cluster_code=TRG000038&work_order_number=WO%2FKUTAI%20KARTANEGARA%2F2026%2FINST%2F10%2F8313&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:31 | TRG000038 | LOA IPUH RT 71 SAMPAI 75 KUTAI KARTANEGARA | WO/KUTAI KARTANEGARA/2026/INST/10/8313 | ATP SUBFEEDER - CW ATP | SUBFEEDER | CW ATP | - | subfeeder_redline | Redline Subfeeder | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/subfeeder/list/by-invoice-phase/cw-atp?cluster_code=TRG000038&work_order_number=WO%2FKUTAI%20KARTANEGARA%2F2026%2FINST%2F10%2F8313&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:32 | TRG000038 | LOA IPUH RT 71 SAMPAI 75 KUTAI KARTANEGARA | WO/KUTAI KARTANEGARA/2026/INST/10/8313 | ATP SUBFEEDER - FULL OPM | SUBFEEDER | FULL OPM | - | subfeeder_opm_otdr_acceptance_test | OPM / OTDR Subfeeder | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/subfeeder/list/by-invoice-phase/full-opm?cluster_code=TRG000038&work_order_number=WO%2FKUTAI%20KARTANEGARA%2F2026%2FINST%2F10%2F8313&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:32 | TRG000038 | LOA IPUH RT 71 SAMPAI 75 KUTAI KARTANEGARA | WO/KUTAI KARTANEGARA/2026/INST/10/8313 | ATP SUBFEEDER - RFS | SUBFEEDER | RFS | - | as_built_drawing_core_management_subfeeder | ABD Core Management Subfeeder | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/subfeeder/list/by-invoice-phase/rfs?cluster_code=TRG000038&work_order_number=WO%2FKUTAI%20KARTANEGARA%2F2026%2FINST%2F10%2F8313&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:32 | TRG000038 | LOA IPUH RT 71 SAMPAI 75 KUTAI KARTANEGARA | WO/KUTAI KARTANEGARA/2026/INST/10/8313 | ATP SUBFEEDER - RFS | SUBFEEDER | RFS | - | as_build_drawing_subfeeder_dwg | ABD Subfeeder dwg | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/subfeeder/list/by-invoice-phase/rfs?cluster_code=TRG000038&work_order_number=WO%2FKUTAI%20KARTANEGARA%2F2026%2FINST%2F10%2F8313&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:32 | TRG000038 | LOA IPUH RT 71 SAMPAI 75 KUTAI KARTANEGARA | WO/KUTAI KARTANEGARA/2026/INST/10/8313 | ATP SUBFEEDER - RFS | SUBFEEDER | RFS | - | as_built_drawing_subfeeder_kmz | ABD Subfeeder kmz | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/subfeeder/list/by-invoice-phase/rfs?cluster_code=TRG000038&work_order_number=WO%2FKUTAI%20KARTANEGARA%2F2026%2FINST%2F10%2F8313&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:32 | TRG000038 | LOA IPUH RT 71 SAMPAI 75 KUTAI KARTANEGARA | WO/KUTAI KARTANEGARA/2026/INST/10/8313 | ATP SUBFEEDER - RFS | SUBFEEDER | RFS | - | build_of_quantity_subfeeder_as_built_drawing | BoQ Subfeeder ABD | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/subfeeder/list/by-invoice-phase/rfs?cluster_code=TRG000038&work_order_number=WO%2FKUTAI%20KARTANEGARA%2F2026%2FINST%2F10%2F8313&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:32 | TRG000038 | LOA IPUH RT 71 SAMPAI 75 KUTAI KARTANEGARA | WO/KUTAI KARTANEGARA/2026/INST/10/8313 | ATP SUBFEEDER - RFS | SUBFEEDER | RFS | - | build_of_quantity_subfeeder_as_plan_drawing | BoQ Subfeeder APD | ON REVIEW | 1 | 2026-08-06 12:38 | [5 empty] | build_of_quantity_subfeeder_as_plan_drawing_TRG000038_20260806123811_TRG000035 APD BOQ SUBFEEDER LOA IPUH RT 71 SAMPAI 75 KUTAI KARTANEGARA.xlsx | https://astri.morarepublic.co.id/rfs-document/subfeeder/list/by-invoice-phase/rfs?cluster_code=TRG000038&work_order_number=WO%2FKUTAI%20KARTANEGARA%2F2026%2FINST%2F10%2F8313&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:32 | TRG000038 | LOA IPUH RT 71 SAMPAI 75 KUTAI KARTANEGARA | WO/KUTAI KARTANEGARA/2026/INST/10/8313 | ATP SUBFEEDER - RFS | SUBFEEDER | RFS | - | justifikasi_berita_acara_opname | Justifikasi Berita Acara Opname | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/subfeeder/list/by-invoice-phase/rfs?cluster_code=TRG000038&work_order_number=WO%2FKUTAI%20KARTANEGARA%2F2026%2FINST%2F10%2F8313&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:32 | TRG000038 | LOA IPUH RT 71 SAMPAI 75 KUTAI KARTANEGARA | WO/KUTAI KARTANEGARA/2026/INST/10/8313 | ATP SUBFEEDER - RFS | SUBFEEDER | RFS | - | subfeeder_project_opname | Project Opname Subfeeder | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/subfeeder/list/by-invoice-phase/rfs?cluster_code=TRG000038&work_order_number=WO%2FKUTAI%20KARTANEGARA%2F2026%2FINST%2F10%2F8313&vendor_label=Technology%20Karya%20Mandiri

## Cluster_Status
scraped_at | cluster_code | clean_list_name | work_order_number | vendor_label | area | status_rfs | document_cw_atp_status | document_full_opm_status | document_rfs_status | document_fac_status | worst_document_status | summary_source_url
2026-08-19 17:30 | TRG000038 | LOA IPUH RT 71 SAMPAI 75 KUTAI KARTANEGARA | WO/KUTAI KARTANEGARA/2026/INST/10/8313 | Technology Karya Mandiri | KUTAI KARTANEGARA |  | - | - | - | - | UNKNOWN | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=TRG000038&work_order_number=WO%2FKUTAI%20KARTANEGARA%2F2026%2FINST%2F10%2F8313&vendor_label=Technology%20Karya%20Mandiri