## Astri_Status
scraped_at | route | scope | phase | cluster_code | clean_list_name | work_order_number | vendor_label | astri_type | astri_label | derived_status | file_count | upload_date | verified_by | verified_at | revision_by | revision_at | revision_remark | filename | detail_url
2026-08-19 17:03 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | PBL000343 | RONDOKUNING RW 03 PROBOLINGGO | WO/PROBOLINGGO/2026/INST/10/8311 | Technology Karya Mandiri | as_plan_drawing_dwg | APD DWG Cluster | APPROVED | 1 | 2026-07-17 10:28 | dwi.mahardianto |  |  |  |  | as_plan_drawing_dwg_PBL000343_20260717102755_APD RONDOKUNING RW 03 PROBOLINGGO.dwg | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=PBL000343&work_order_number=WO%2FPROBOLINGGO%2F2026%2FINST%2F10%2F8311&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:03 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | PBL000343 | RONDOKUNING RW 03 PROBOLINGGO | WO/PROBOLINGGO/2026/INST/10/8311 | Technology Karya Mandiri | as_plan_drawing_kmz | APD KMZ Cluster | APPROVED | 1 | 2026-07-17 10:28 | dwi.mahardianto |  |  |  |  | as_plan_drawing_kmz_PBL000343_20260717102755_PBL000343.kmz | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=PBL000343&work_order_number=WO%2FPROBOLINGGO%2F2026%2FINST%2F10%2F8311&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:03 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | PBL000343 | RONDOKUNING RW 03 PROBOLINGGO | WO/PROBOLINGGO/2026/INST/10/8311 | Technology Karya Mandiri | as_plan_drawing_subfeeder_kmz | APD Subfeeder kmz | APPROVED | 1 | 2026-07-28 14:54 | dwi.mahardianto |  |  |  |  | as_plan_drawing_subfeeder_kmz_PBL000343_20260728145358_SF PBL000343.kmz | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=PBL000343&work_order_number=WO%2FPROBOLINGGO%2F2026%2FINST%2F10%2F8311&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:03 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | PBL000343 | RONDOKUNING RW 03 PROBOLINGGO | WO/PROBOLINGGO/2026/INST/10/8311 | Technology Karya Mandiri | permit_subfeeder | BA Permit Subfeeder | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=PBL000343&work_order_number=WO%2FPROBOLINGGO%2F2026%2FINST%2F10%2F8311&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:03 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | PBL000343 | RONDOKUNING RW 03 PROBOLINGGO | WO/PROBOLINGGO/2026/INST/10/8311 | Technology Karya Mandiri | permit_cluster_aggreement | Berita Acara Kesepakatan | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=PBL000343&work_order_number=WO%2FPROBOLINGGO%2F2026%2FINST%2F10%2F8311&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:03 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | PBL000343 | RONDOKUNING RW 03 PROBOLINGGO | WO/PROBOLINGGO/2026/INST/10/8311 | Technology Karya Mandiri | permit_open | Berita Acara Open | APPROVED | 1 | 2025-12-08 10:41 | Sari | 2026-07-10 19:17 |  |  |  | permit_open_PBL000343_20251208104107_BA_Open_Rondokuning_RW_03.pdf | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=PBL000343&work_order_number=WO%2FPROBOLINGGO%2F2026%2FINST%2F10%2F8311&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:03 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | PBL000343 | RONDOKUNING RW 03 PROBOLINGGO | WO/PROBOLINGGO/2026/INST/10/8311 | Technology Karya Mandiri | donation_approval | Cluster Approval Proposal | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=PBL000343&work_order_number=WO%2FPROBOLINGGO%2F2026%2FINST%2F10%2F8311&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:03 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | PBL000343 | RONDOKUNING RW 03 PROBOLINGGO | WO/PROBOLINGGO/2026/INST/10/8311 | Technology Karya Mandiri | civil_work_acceptance_test | CW ATP | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=PBL000343&work_order_number=WO%2FPROBOLINGGO%2F2026%2FINST%2F10%2F8311&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:03 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | PBL000343 | RONDOKUNING RW 03 PROBOLINGGO | WO/PROBOLINGGO/2026/INST/10/8311 | Technology Karya Mandiri | subfeeder_civil_work_acceptance_test | CW ATP Subfeeder | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=PBL000343&work_order_number=WO%2FPROBOLINGGO%2F2026%2FINST%2F10%2F8311&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:03 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | PBL000343 | RONDOKUNING RW 03 PROBOLINGGO | WO/PROBOLINGGO/2026/INST/10/8311 | Technology Karya Mandiri | cluster_survey_form | Form Cluster Survey | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=PBL000343&work_order_number=WO%2FPROBOLINGGO%2F2026%2FINST%2F10%2F8311&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:03 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | PBL000343 | RONDOKUNING RW 03 PROBOLINGGO | WO/PROBOLINGGO/2026/INST/10/8311 | Technology Karya Mandiri | permit_vip_form | Form Free Layanan | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=PBL000343&work_order_number=WO%2FPROBOLINGGO%2F2026%2FINST%2F10%2F8311&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:03 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | PBL000343 | RONDOKUNING RW 03 PROBOLINGGO | WO/PROBOLINGGO/2026/INST/10/8311 | Technology Karya Mandiri | homepass_database | Homepass Database | APPROVED | 1 | 2026-07-17 10:28 | dwi.mahardianto |  |  |  |  | homepass_database_PBL000343_20260717102754_05. APD HPDB RONDOKUNING RW 03 PROBOLINGGO.xlsx | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=PBL000343&work_order_number=WO%2FPROBOLINGGO%2F2026%2FINST%2F10%2F8311&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:03 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | PBL000343 | RONDOKUNING RW 03 PROBOLINGGO | WO/PROBOLINGGO/2026/INST/10/8311 | Technology Karya Mandiri | rough_design_layout | Layout SnD Kasar | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=PBL000343&work_order_number=WO%2FPROBOLINGGO%2F2026%2FINST%2F10%2F8311&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:03 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | PBL000343 | RONDOKUNING RW 03 PROBOLINGGO | WO/PROBOLINGGO/2026/INST/10/8311 | Technology Karya Mandiri | sales_validation_layout | Layout Validasi Sales | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=PBL000343&work_order_number=WO%2FPROBOLINGGO%2F2026%2FINST%2F10%2F8311&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:03 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | PBL000343 | RONDOKUNING RW 03 PROBOLINGGO | WO/PROBOLINGGO/2026/INST/10/8311 | Technology Karya Mandiri | ptsp | PTSP | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=PBL000343&work_order_number=WO%2FPROBOLINGGO%2F2026%2FINST%2F10%2F8311&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:03 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | PBL000343 | RONDOKUNING RW 03 PROBOLINGGO | WO/PROBOLINGGO/2026/INST/10/8311 | Technology Karya Mandiri | redline | Redline | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=PBL000343&work_order_number=WO%2FPROBOLINGGO%2F2026%2FINST%2F10%2F8311&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:03 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | PBL000343 | RONDOKUNING RW 03 PROBOLINGGO | WO/PROBOLINGGO/2026/INST/10/8311 | Technology Karya Mandiri | subfeeder_redline | Redline Subfeeder | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=PBL000343&work_order_number=WO%2FPROBOLINGGO%2F2026%2FINST%2F10%2F8311&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:03 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | PBL000343 | RONDOKUNING RW 03 PROBOLINGGO | WO/PROBOLINGGO/2026/INST/10/8311 | Technology Karya Mandiri | rekomtek | Rekomtek | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=PBL000343&work_order_number=WO%2FPROBOLINGGO%2F2026%2FINST%2F10%2F8311&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:03 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | PBL000343 | RONDOKUNING RW 03 PROBOLINGGO | WO/PROBOLINGGO/2026/INST/10/8311 | Technology Karya Mandiri | tssr | TSSR | APPROVED | 1 | 2026-07-17 10:28 | dwi.mahardianto |  |  |  |  | tssr_PBL000343_20260717102756_PBL000343 TSSR RONDOKUNING RW 03 PROBOLINGGO.pdf | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=PBL000343&work_order_number=WO%2FPROBOLINGGO%2F2026%2FINST%2F10%2F8311&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:03 | ATP CLUSTER - FULL OPM | CLUSTER | FULL OPM | PBL000343 | RONDOKUNING RW 03 PROBOLINGGO | WO/PROBOLINGGO/2026/INST/10/8311 | Technology Karya Mandiri | opm_otdr_acceptance_test | OPM / OTDR ATP | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/full-opm?cluster_code=PBL000343&work_order_number=WO%2FPROBOLINGGO%2F2026%2FINST%2F10%2F8311&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:04 | ATP CLUSTER - RFS | CLUSTER | RFS | PBL000343 | RONDOKUNING RW 03 PROBOLINGGO | WO/PROBOLINGGO/2026/INST/10/8311 | Technology Karya Mandiri | build_of_quantity_as_built_drawing | ABD BoQ Cluster | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/rfs?cluster_code=PBL000343&work_order_number=WO%2FPROBOLINGGO%2F2026%2FINST%2F10%2F8311&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:04 | ATP CLUSTER - RFS | CLUSTER | RFS | PBL000343 | RONDOKUNING RW 03 PROBOLINGGO | WO/PROBOLINGGO/2026/INST/10/8311 | Technology Karya Mandiri | as_built_drawing_dwg | ABD Cluster DWG | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/rfs?cluster_code=PBL000343&work_order_number=WO%2FPROBOLINGGO%2F2026%2FINST%2F10%2F8311&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:04 | ATP CLUSTER - RFS | CLUSTER | RFS | PBL000343 | RONDOKUNING RW 03 PROBOLINGGO | WO/PROBOLINGGO/2026/INST/10/8311 | Technology Karya Mandiri | as_built_drawing_kmz | ABD Cluster KMZ | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/rfs?cluster_code=PBL000343&work_order_number=WO%2FPROBOLINGGO%2F2026%2FINST%2F10%2F8311&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:04 | ATP CLUSTER - RFS | CLUSTER | RFS | PBL000343 | RONDOKUNING RW 03 PROBOLINGGO | WO/PROBOLINGGO/2026/INST/10/8311 | Technology Karya Mandiri | build_of_quantity_as_plan_drawing | BoQ APD | APPROVED | 1 | 2026-07-17 10:28 | dwi.mahardianto |  |  |  |  | build_of_quantity_as_plan_drawing_PBL000343_20260717102756_APD BOQ RONDOKUNING RW 03 PROBOLINGGO.xlsx | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/rfs?cluster_code=PBL000343&work_order_number=WO%2FPROBOLINGGO%2F2026%2FINST%2F10%2F8311&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:04 | ATP CLUSTER - RFS | CLUSTER | RFS | PBL000343 | RONDOKUNING RW 03 PROBOLINGGO | WO/PROBOLINGGO/2026/INST/10/8311 | Technology Karya Mandiri | core_management | Core Management | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/rfs?cluster_code=PBL000343&work_order_number=WO%2FPROBOLINGGO%2F2026%2FINST%2F10%2F8311&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:04 | ATP CLUSTER - RFS | CLUSTER | RFS | PBL000343 | RONDOKUNING RW 03 PROBOLINGGO | WO/PROBOLINGGO/2026/INST/10/8311 | Technology Karya Mandiri | justifikasi_berita_acara_opname | Justifikasi Berita Acara Opname | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/rfs?cluster_code=PBL000343&work_order_number=WO%2FPROBOLINGGO%2F2026%2FINST%2F10%2F8311&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:04 | ATP CLUSTER - RFS | CLUSTER | RFS | PBL000343 | RONDOKUNING RW 03 PROBOLINGGO | WO/PROBOLINGGO/2026/INST/10/8311 | Technology Karya Mandiri | project_opname | Project Opname | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/rfs?cluster_code=PBL000343&work_order_number=WO%2FPROBOLINGGO%2F2026%2FINST%2F10%2F8311&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:04 | ATP CLUSTER - RFS | CLUSTER | RFS | PBL000343 | RONDOKUNING RW 03 PROBOLINGGO | WO/PROBOLINGGO/2026/INST/10/8311 | Technology Karya Mandiri | subfeeder_project_opname | Project Opname Subfeeder | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/rfs?cluster_code=PBL000343&work_order_number=WO%2FPROBOLINGGO%2F2026%2FINST%2F10%2F8311&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:04 | PROJECT OPNAME - CLUSTER | CLUSTER | PROJECT OPNAME | PBL000343 |  | WO/PROBOLINGGO/2026/INST/10/8311 | Technology Karya Mandiri |  |  | PROJECT_OPNAME_NOT_FOUND
2026-08-19 17:04 | ATP SUBFEEDER - CW ATP | SUBFEEDER | CW ATP | PBL000343 | RONDOKUNING RW 03 PROBOLINGGO | WO/PROBOLINGGO/2026/INST/10/8311 | Technology Karya Mandiri | as_plan_drawing_core_management_subfeeder | APD Core Management Subfeeder | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/subfeeder/list/by-invoice-phase/cw-atp?cluster_code=PBL000343&work_order_number=WO%2FPROBOLINGGO%2F2026%2FINST%2F10%2F8311&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:04 | ATP SUBFEEDER - CW ATP | SUBFEEDER | CW ATP | PBL000343 | RONDOKUNING RW 03 PROBOLINGGO | WO/PROBOLINGGO/2026/INST/10/8311 | Technology Karya Mandiri | as_plan_drawing_subfeeder_dwg | APD Subfeeder dwg | APPROVED | 1 | 2026-07-28 14:54 | dwi.mahardianto |  |  |  |  | as_plan_drawing_subfeeder_dwg_PBL000343_20260728145358_APD SF RONDOKUNING RW 03 PROBOLINGGO.dwg | https://astri.morarepublic.co.id/rfs-document/subfeeder/list/by-invoice-phase/cw-atp?cluster_code=PBL000343&work_order_number=WO%2FPROBOLINGGO%2F2026%2FINST%2F10%2F8311&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:04 | ATP SUBFEEDER - CW ATP | SUBFEEDER | CW ATP | PBL000343 | RONDOKUNING RW 03 PROBOLINGGO | WO/PROBOLINGGO/2026/INST/10/8311 | Technology Karya Mandiri | as_plan_drawing_subfeeder_kmz | APD Subfeeder kmz | APPROVED | 1 | 2026-07-28 14:54 | dwi.mahardianto |  |  |  |  | as_plan_drawing_subfeeder_kmz_PBL000343_20260728145358_SF PBL000343.kmz | https://astri.morarepublic.co.id/rfs-document/subfeeder/list/by-invoice-phase/cw-atp?cluster_code=PBL000343&work_order_number=WO%2FPROBOLINGGO%2F2026%2FINST%2F10%2F8311&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:04 | ATP SUBFEEDER - CW ATP | SUBFEEDER | CW ATP | PBL000343 | RONDOKUNING RW 03 PROBOLINGGO | WO/PROBOLINGGO/2026/INST/10/8311 | Technology Karya Mandiri | permit_subfeeder | BA Permit Subfeeder | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/subfeeder/list/by-invoice-phase/cw-atp?cluster_code=PBL000343&work_order_number=WO%2FPROBOLINGGO%2F2026%2FINST%2F10%2F8311&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:04 | ATP SUBFEEDER - CW ATP | SUBFEEDER | CW ATP | PBL000343 | RONDOKUNING RW 03 PROBOLINGGO | WO/PROBOLINGGO/2026/INST/10/8311 | Technology Karya Mandiri | subfeeder_civil_work_acceptance_test | CW ATP Subfeeder | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/subfeeder/list/by-invoice-phase/cw-atp?cluster_code=PBL000343&work_order_number=WO%2FPROBOLINGGO%2F2026%2FINST%2F10%2F8311&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:04 | ATP SUBFEEDER - CW ATP | SUBFEEDER | CW ATP | PBL000343 | RONDOKUNING RW 03 PROBOLINGGO | WO/PROBOLINGGO/2026/INST/10/8311 | Technology Karya Mandiri | subfeeder_redline | Redline Subfeeder | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/subfeeder/list/by-invoice-phase/cw-atp?cluster_code=PBL000343&work_order_number=WO%2FPROBOLINGGO%2F2026%2FINST%2F10%2F8311&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:04 | ATP SUBFEEDER - FULL OPM | SUBFEEDER | FULL OPM | PBL000343 | RONDOKUNING RW 03 PROBOLINGGO | WO/PROBOLINGGO/2026/INST/10/8311 | Technology Karya Mandiri | subfeeder_opm_otdr_acceptance_test | OPM / OTDR Subfeeder | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/subfeeder/list/by-invoice-phase/full-opm?cluster_code=PBL000343&work_order_number=WO%2FPROBOLINGGO%2F2026%2FINST%2F10%2F8311&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:04 | ATP SUBFEEDER - RFS | SUBFEEDER | RFS | PBL000343 | RONDOKUNING RW 03 PROBOLINGGO | WO/PROBOLINGGO/2026/INST/10/8311 | Technology Karya Mandiri | as_built_drawing_core_management_subfeeder | ABD Core Management Subfeeder | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/subfeeder/list/by-invoice-phase/rfs?cluster_code=PBL000343&work_order_number=WO%2FPROBOLINGGO%2F2026%2FINST%2F10%2F8311&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:04 | ATP SUBFEEDER - RFS | SUBFEEDER | RFS | PBL000343 | RONDOKUNING RW 03 PROBOLINGGO | WO/PROBOLINGGO/2026/INST/10/8311 | Technology Karya Mandiri | as_build_drawing_subfeeder_dwg | ABD Subfeeder dwg | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/subfeeder/list/by-invoice-phase/rfs?cluster_code=PBL000343&work_order_number=WO%2FPROBOLINGGO%2F2026%2FINST%2F10%2F8311&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:04 | ATP SUBFEEDER - RFS | SUBFEEDER | RFS | PBL000343 | RONDOKUNING RW 03 PROBOLINGGO | WO/PROBOLINGGO/2026/INST/10/8311 | Technology Karya Mandiri | as_built_drawing_subfeeder_kmz | ABD Subfeeder kmz | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/subfeeder/list/by-invoice-phase/rfs?cluster_code=PBL000343&work_order_number=WO%2FPROBOLINGGO%2F2026%2FINST%2F10%2F8311&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:04 | ATP SUBFEEDER - RFS | SUBFEEDER | RFS | PBL000343 | RONDOKUNING RW 03 PROBOLINGGO | WO/PROBOLINGGO/2026/INST/10/8311 | Technology Karya Mandiri | build_of_quantity_subfeeder_as_built_drawing | BoQ Subfeeder ABD | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/subfeeder/list/by-invoice-phase/rfs?cluster_code=PBL000343&work_order_number=WO%2FPROBOLINGGO%2F2026%2FINST%2F10%2F8311&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:04 | ATP SUBFEEDER - RFS | SUBFEEDER | RFS | PBL000343 | RONDOKUNING RW 03 PROBOLINGGO | WO/PROBOLINGGO/2026/INST/10/8311 | Technology Karya Mandiri | build_of_quantity_subfeeder_as_plan_drawing | BoQ Subfeeder APD | APPROVED | 1 | 2026-07-28 14:54 | dwi.mahardianto |  |  |  |  | build_of_quantity_subfeeder_as_plan_drawing_PBL000343_20260728145359_APD BOQ SF RONDOKUNING RW 03 PROBOLINGGO.xlsx | https://astri.morarepublic.co.id/rfs-document/subfeeder/list/by-invoice-phase/rfs?cluster_code=PBL000343&work_order_number=WO%2FPROBOLINGGO%2F2026%2FINST%2F10%2F8311&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:04 | ATP SUBFEEDER - RFS | SUBFEEDER | RFS | PBL000343 | RONDOKUNING RW 03 PROBOLINGGO | WO/PROBOLINGGO/2026/INST/10/8311 | Technology Karya Mandiri | justifikasi_berita_acara_opname | Justifikasi Berita Acara Opname | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/subfeeder/list/by-invoice-phase/rfs?cluster_code=PBL000343&work_order_number=WO%2FPROBOLINGGO%2F2026%2FINST%2F10%2F8311&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:04 | ATP SUBFEEDER - RFS | SUBFEEDER | RFS | PBL000343 | RONDOKUNING RW 03 PROBOLINGGO | WO/PROBOLINGGO/2026/INST/10/8311 | Technology Karya Mandiri | subfeeder_project_opname | Project Opname Subfeeder | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/subfeeder/list/by-invoice-phase/rfs?cluster_code=PBL000343&work_order_number=WO%2FPROBOLINGGO%2F2026%2FINST%2F10%2F8311&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:04 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | as_plan_drawing_dwg | APD DWG Cluster | APPROVED | 1 | 2026-08-04 11:43 | ifam.famula |  |  |  |  | as_plan_drawing_dwg_BLT000695_20260804114328_BLT000695 DWG APD BENCE RW 06 BLITAR.dwg | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:04 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | as_plan_drawing_kmz | APD KMZ Cluster | APPROVED | 3 | 2026-08-10 11:48 | ifam.famula |  |  |  |  | as_plan_drawing_kmz_BLT000695_20260810114823_BLT000695 KMZ APD BENCE RW 06 BLITAR.kmz | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:04 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | as_plan_drawing_subfeeder_kmz | APD Subfeeder kmz | APPROVED | 2 | 2026-08-10 12:30 | ifam.famula |  |  |  |  | as_plan_drawing_subfeeder_kmz_BLT000695_20260810122940_BLT000695 KMZ SF APD BENCE RW 06 BLITAR.KMZ | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:04 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | permit_subfeeder | BA Permit Subfeeder | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:04 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | permit_cluster_aggreement | Berita Acara Kesepakatan | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:04 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | permit_open | Berita Acara Open | ON REVIEW | 1 | 2026-08-10 10:34 | [5 empty] | permit_open_BLT000695_20260810103330_BA_OPEN_BENCE_RW_06_BLITAR.pdf | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:04 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | donation_approval | Cluster Approval Proposal | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:04 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | civil_work_acceptance_test | CW ATP | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:04 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | subfeeder_civil_work_acceptance_test | CW ATP Subfeeder | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:04 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | cluster_survey_form | Form Cluster Survey | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:04 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | permit_vip_form | Form Free Layanan | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:04 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | homepass_database | Homepass Database | APPROVED | 1 | 2026-08-04 11:43 | ifam.famula |  |  |  |  | homepass_database_BLT000695_20260804114328_BLT000695 HPDB APD BENCE RW 06 BLITAR.xlsx | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:04 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | rough_design_layout | Layout SnD Kasar | ON REVIEW | 1 | 2026-08-10 10:34 | [5 empty] | rough_design_layout_BLT000695_20260810103331_Hasil Valsal Cluster BENCE RW 06 BLITAR.pdf | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:04 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | sales_validation_layout | Layout Validasi Sales | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:04 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | ptsp | PTSP | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:04 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | redline | Redline | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:04 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | subfeeder_redline | Redline Subfeeder | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:04 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | rekomtek | Rekomtek | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:04 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | tssr | TSSR | APPROVED | 1 | 2026-08-04 11:44 | ifam.famula |  |  |  |  | tssr_BLT000695_20260804114330_BLT000695 TSSR BENCE RW 06 BLITAR.pdf | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:05 | ATP CLUSTER - FULL OPM | CLUSTER | FULL OPM | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | opm_otdr_acceptance_test | OPM / OTDR ATP | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/full-opm?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:05 | ATP CLUSTER - RFS | CLUSTER | RFS | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | build_of_quantity_as_built_drawing | ABD BoQ Cluster | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/rfs?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:05 | ATP CLUSTER - RFS | CLUSTER | RFS | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | as_built_drawing_dwg | ABD Cluster DWG | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/rfs?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:05 | ATP CLUSTER - RFS | CLUSTER | RFS | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | as_built_drawing_kmz | ABD Cluster KMZ | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/rfs?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:05 | ATP CLUSTER - RFS | CLUSTER | RFS | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | build_of_quantity_as_plan_drawing | BoQ APD | APPROVED | 1 | 2026-08-04 11:44 | ifam.famula |  |  |  |  | build_of_quantity_as_plan_drawing_BLT000695_20260804114329_BLT000695 BOQ APD BENCE RW 06 BLITAR.xlsx | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/rfs?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:05 | ATP CLUSTER - RFS | CLUSTER | RFS | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | core_management | Core Management | ON REVIEW | 1 | 2026-08-19 15:54 | [5 empty] | core_management_BLT000695_20260819155348_BLT000695 HPDB PRE ABD BENCE RW 06 BLITAR.xlsx | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/rfs?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:05 | ATP CLUSTER - RFS | CLUSTER | RFS | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | justifikasi_berita_acara_opname | Justifikasi Berita Acara Opname | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/rfs?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:05 | ATP CLUSTER - RFS | CLUSTER | RFS | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | project_opname | Project Opname | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/rfs?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:05 | ATP CLUSTER - RFS | CLUSTER | RFS | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | subfeeder_project_opname | Project Opname Subfeeder | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/rfs?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:05 | PROJECT OPNAME - CLUSTER | CLUSTER | PROJECT OPNAME | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | build_of_quantity_as_built_drawing | ABD BoQ Cluster | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/material/cluster/project-opname/review?cluster_code=BLT000695&work_order_number=WO/ALL/2026/DOCU/16/80008&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:05 | PROJECT OPNAME - CLUSTER | CLUSTER | PROJECT OPNAME | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | as_built_drawing_dwg | ABD Cluster DWG | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/material/cluster/project-opname/review?cluster_code=BLT000695&work_order_number=WO/ALL/2026/DOCU/16/80008&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:05 | PROJECT OPNAME - CLUSTER | CLUSTER | PROJECT OPNAME | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | as_built_drawing_kmz | ABD Cluster KMZ | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/material/cluster/project-opname/review?cluster_code=BLT000695&work_order_number=WO/ALL/2026/DOCU/16/80008&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:05 | PROJECT OPNAME - CLUSTER | CLUSTER | PROJECT OPNAME | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | build_of_quantity_as_plan_drawing | BoQ APD | APPROVED | 1 | 2026-08-04 11:44 | ifam.famula |  |  |  |  | build_of_quantity_as_plan_drawing_BLT000695_20260804114329_BLT000695 BOQ APD BENCE RW 06 BLITAR.xlsx | https://astri.morarepublic.co.id/material/cluster/project-opname/review?cluster_code=BLT000695&work_order_number=WO/ALL/2026/DOCU/16/80008&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:05 | PROJECT OPNAME - CLUSTER | CLUSTER | PROJECT OPNAME | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | build_of_quantity_project_opname | BOQ Project Opname | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/material/cluster/project-opname/review?cluster_code=BLT000695&work_order_number=WO/ALL/2026/DOCU/16/80008&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:05 | PROJECT OPNAME - CLUSTER | CLUSTER | PROJECT OPNAME | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | justifikasi_berita_acara_opname | Justifikasi Berita Acara Opname | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/material/cluster/project-opname/review?cluster_code=BLT000695&work_order_number=WO/ALL/2026/DOCU/16/80008&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:05 | PROJECT OPNAME - CLUSTER | CLUSTER | PROJECT OPNAME | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | opm_otdr_acceptance_test | OPM / OTDR ATP | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/material/cluster/project-opname/review?cluster_code=BLT000695&work_order_number=WO/ALL/2026/DOCU/16/80008&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:05 | PROJECT OPNAME - CLUSTER | CLUSTER | PROJECT OPNAME | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | project_opname | Project Opname | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/material/cluster/project-opname/review?cluster_code=BLT000695&work_order_number=WO/ALL/2026/DOCU/16/80008&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:05 | ATP SUBFEEDER - CW ATP | SUBFEEDER | CW ATP | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | as_plan_drawing_core_management_subfeeder | APD Core Management Subfeeder | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/subfeeder/list/by-invoice-phase/cw-atp?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:05 | ATP SUBFEEDER - CW ATP | SUBFEEDER | CW ATP | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | as_plan_drawing_subfeeder_dwg | APD Subfeeder dwg | APPROVED | 1 | 2026-08-04 12:06 | ifam.famula |  |  |  |  | as_plan_drawing_subfeeder_dwg_BLT000695_20260804120542_BLT000695 DWG SF APD BENCE RW 06 BLITAR.dwg | https://astri.morarepublic.co.id/rfs-document/subfeeder/list/by-invoice-phase/cw-atp?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:05 | ATP SUBFEEDER - CW ATP | SUBFEEDER | CW ATP | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | as_plan_drawing_subfeeder_kmz | APD Subfeeder kmz | APPROVED | 2 | 2026-08-10 12:30 | ifam.famula |  |  |  |  | as_plan_drawing_subfeeder_kmz_BLT000695_20260810122940_BLT000695 KMZ SF APD BENCE RW 06 BLITAR.KMZ | https://astri.morarepublic.co.id/rfs-document/subfeeder/list/by-invoice-phase/cw-atp?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:05 | ATP SUBFEEDER - CW ATP | SUBFEEDER | CW ATP | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | permit_subfeeder | BA Permit Subfeeder | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/subfeeder/list/by-invoice-phase/cw-atp?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:05 | ATP SUBFEEDER - CW ATP | SUBFEEDER | CW ATP | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | subfeeder_civil_work_acceptance_test | CW ATP Subfeeder | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/subfeeder/list/by-invoice-phase/cw-atp?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:05 | ATP SUBFEEDER - CW ATP | SUBFEEDER | CW ATP | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | subfeeder_redline | Redline Subfeeder | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/subfeeder/list/by-invoice-phase/cw-atp?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:05 | ATP SUBFEEDER - FULL OPM | SUBFEEDER | FULL OPM | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | subfeeder_opm_otdr_acceptance_test | OPM / OTDR Subfeeder | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/subfeeder/list/by-invoice-phase/full-opm?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:08 | ATP SUBFEEDER - RFS | SUBFEEDER | RFS | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | as_built_drawing_core_management_subfeeder | ABD Core Management Subfeeder | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/subfeeder/list/by-invoice-phase/rfs?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:08 | ATP SUBFEEDER - RFS | SUBFEEDER | RFS | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | as_build_drawing_subfeeder_dwg | ABD Subfeeder dwg | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/subfeeder/list/by-invoice-phase/rfs?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:08 | ATP SUBFEEDER - RFS | SUBFEEDER | RFS | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | as_built_drawing_subfeeder_kmz | ABD Subfeeder kmz | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/subfeeder/list/by-invoice-phase/rfs?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:08 | ATP SUBFEEDER - RFS | SUBFEEDER | RFS | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | build_of_quantity_subfeeder_as_built_drawing | BoQ Subfeeder ABD | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/subfeeder/list/by-invoice-phase/rfs?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:08 | ATP SUBFEEDER - RFS | SUBFEEDER | RFS | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | build_of_quantity_subfeeder_as_plan_drawing | BoQ Subfeeder APD | APPROVED | 1 | 2026-08-04 12:06 | ifam.famula |  |  |  |  | build_of_quantity_subfeeder_as_plan_drawing_BLT000695_20260804120543_BLT000695 BOQ SF APD BENCE RW 06 BLITAR.xlsx | https://astri.morarepublic.co.id/rfs-document/subfeeder/list/by-invoice-phase/rfs?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:08 | ATP SUBFEEDER - RFS | SUBFEEDER | RFS | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | justifikasi_berita_acara_opname | Justifikasi Berita Acara Opname | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/subfeeder/list/by-invoice-phase/rfs?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:08 | ATP SUBFEEDER - RFS | SUBFEEDER | RFS | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | subfeeder_project_opname | Project Opname Subfeeder | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/subfeeder/list/by-invoice-phase/rfs?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:08 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | BLT000250 | TAWANGSARI RW 04 BLITAR | WO/BLITAR/2026/INST/10/8305 | Technology Karya Mandiri | as_plan_drawing_dwg | APD DWG Cluster | APPROVED | 1 | 2026-07-30 16:07 | ifam.famula |  |  |  |  | as_plan_drawing_dwg_BLT000250_20260730160707_BLT000250 DWG APD TAWANGSARI RW 04 BLITAR.dwg | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=BLT000250&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8305&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:08 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | BLT000250 | TAWANGSARI RW 04 BLITAR | WO/BLITAR/2026/INST/10/8305 | Technology Karya Mandiri | as_plan_drawing_kmz | APD KMZ Cluster | APPROVED | 1 | 2026-07-30 16:07 | ifam.famula |  |  |  |  | as_plan_drawing_kmz_BLT000250_20260730160707_BLT000250 KMZ APD TAWANGSARI RW 04 BLITAR.KMZ | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=BLT000250&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8305&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:08 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | BLT000250 | TAWANGSARI RW 04 BLITAR | WO/BLITAR/2026/INST/10/8305 | Technology Karya Mandiri | as_plan_drawing_subfeeder_kmz | APD Subfeeder kmz | APPROVED | 2 | 2026-08-03 16:04 | ifam.famula |  |  |  |  | as_plan_drawing_subfeeder_kmz_BLT000250_20260803160424_BLT000250 KMZ APD SF TAWANGSARI RW 04 BLITAR.KMZ | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=BLT000250&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8305&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:08 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | BLT000250 | TAWANGSARI RW 04 BLITAR | WO/BLITAR/2026/INST/10/8305 | Technology Karya Mandiri | permit_subfeeder | BA Permit Subfeeder | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=BLT000250&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8305&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:08 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | BLT000250 | TAWANGSARI RW 04 BLITAR | WO/BLITAR/2026/INST/10/8305 | Technology Karya Mandiri | permit_cluster_aggreement | Berita Acara Kesepakatan | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=BLT000250&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8305&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:08 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | BLT000250 | TAWANGSARI RW 04 BLITAR | WO/BLITAR/2026/INST/10/8305 | Technology Karya Mandiri | permit_open | Berita Acara Open | ON REVIEW | 2 | 2026-08-06 05:02 | [5 empty] | permit_open_BLT000250_20260806050214_BA OPEN Tawangsari RW 04 Blitar.pdf | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=BLT000250&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8305&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:08 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | BLT000250 | TAWANGSARI RW 04 BLITAR | WO/BLITAR/2026/INST/10/8305 | Technology Karya Mandiri | donation_approval | Cluster Approval Proposal | ON REVIEW | 1 | 2026-08-19 13:54 | [5 empty] | donation_approval_BLT000250_20260819135340_CAP TAWANGSARI RW 04 BLITAR.pdf | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=BLT000250&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8305&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:08 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | BLT000250 | TAWANGSARI RW 04 BLITAR | WO/BLITAR/2026/INST/10/8305 | Technology Karya Mandiri | civil_work_acceptance_test | CW ATP | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=BLT000250&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8305&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:08 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | BLT000250 | TAWANGSARI RW 04 BLITAR | WO/BLITAR/2026/INST/10/8305 | Technology Karya Mandiri | subfeeder_civil_work_acceptance_test | CW ATP Subfeeder | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=BLT000250&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8305&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:08 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | BLT000250 | TAWANGSARI RW 04 BLITAR | WO/BLITAR/2026/INST/10/8305 | Technology Karya Mandiri | cluster_survey_form | Form Cluster Survey | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=BLT000250&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8305&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:08 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | BLT000250 | TAWANGSARI RW 04 BLITAR | WO/BLITAR/2026/INST/10/8305 | Technology Karya Mandiri | permit_vip_form | Form Free Layanan | ON REVIEW | 1 | 2026-08-19 13:59 | [5 empty] | permit_vip_form_BLT000250_20260819135847_N.A.pdf | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=BLT000250&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8305&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:08 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | BLT000250 | TAWANGSARI RW 04 BLITAR | WO/BLITAR/2026/INST/10/8305 | Technology Karya Mandiri | homepass_database | Homepass Database | APPROVED | 1 | 2026-07-30 16:07 | ifam.famula |  |  |  |  | homepass_database_BLT000250_20260730160706_BLT000250 HPDB APD TAWANGSARI RW 04 BLITAR.xlsx | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=BLT000250&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8305&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:08 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | BLT000250 | TAWANGSARI RW 04 BLITAR | WO/BLITAR/2026/INST/10/8305 | Technology Karya Mandiri | rough_design_layout | Layout SnD Kasar | ON REVIEW | 2 | 2026-08-06 05:02 | [5 empty] | rough_design_layout_BLT000250_20260806050214_SND KASAR TAWANGSARI RW 04.pdf | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=BLT000250&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8305&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:08 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | BLT000250 | TAWANGSARI RW 04 BLITAR | WO/BLITAR/2026/INST/10/8305 | Technology Karya Mandiri | sales_validation_layout | Layout Validasi Sales | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=BLT000250&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8305&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:08 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | BLT000250 | TAWANGSARI RW 04 BLITAR | WO/BLITAR/2026/INST/10/8305 | Technology Karya Mandiri | ptsp | PTSP | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=BLT000250&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8305&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:08 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | BLT000250 | TAWANGSARI RW 04 BLITAR | WO/BLITAR/2026/INST/10/8305 | Technology Karya Mandiri | redline | Redline | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=BLT000250&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8305&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:08 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | BLT000250 | TAWANGSARI RW 04 BLITAR | WO/BLITAR/2026/INST/10/8305 | Technology Karya Mandiri | subfeeder_redline | Redline Subfeeder | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=BLT000250&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8305&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:08 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | BLT000250 | TAWANGSARI RW 04 BLITAR | WO/BLITAR/2026/INST/10/8305 | Technology Karya Mandiri | rekomtek | Rekomtek | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=BLT000250&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8305&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:08 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | BLT000250 | TAWANGSARI RW 04 BLITAR | WO/BLITAR/2026/INST/10/8305 | Technology Karya Mandiri | tssr | TSSR | APPROVED | 1 | 2026-07-30 16:07 | ifam.famula |  |  |  |  | tssr_BLT000250_20260730160708_BLT000250 TSSR TAWANGSARI RW 04 BLITAR.pdf | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=BLT000250&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8305&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:08 | ATP CLUSTER - FULL OPM | CLUSTER | FULL OPM | BLT000250 | TAWANGSARI RW 04 BLITAR | WO/BLITAR/2026/INST/10/8305 | Technology Karya Mandiri | opm_otdr_acceptance_test | OPM / OTDR ATP | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/full-opm?cluster_code=BLT000250&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8305&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:09 | ATP CLUSTER - RFS | CLUSTER | RFS | BLT000250 | TAWANGSARI RW 04 BLITAR | WO/BLITAR/2026/INST/10/8305 | Technology Karya Mandiri | build_of_quantity_as_built_drawing | ABD BoQ Cluster | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/rfs?cluster_code=BLT000250&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8305&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:09 | ATP CLUSTER - RFS | CLUSTER | RFS | BLT000250 | TAWANGSARI RW 04 BLITAR | WO/BLITAR/2026/INST/10/8305 | Technology Karya Mandiri | as_built_drawing_dwg | ABD Cluster DWG | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/rfs?cluster_code=BLT000250&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8305&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:09 | ATP CLUSTER - RFS | CLUSTER | RFS | BLT000250 | TAWANGSARI RW 04 BLITAR | WO/BLITAR/2026/INST/10/8305 | Technology Karya Mandiri | as_built_drawing_kmz | ABD Cluster KMZ | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/rfs?cluster_code=BLT000250&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8305&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:09 | ATP CLUSTER - RFS | CLUSTER | RFS | BLT000250 | TAWANGSARI RW 04 BLITAR | WO/BLITAR/2026/INST/10/8305 | Technology Karya Mandiri | build_of_quantity_as_plan_drawing | BoQ APD | APPROVED | 1 | 2026-07-31 13:29 | ifam.famula |  |  |  |  | build_of_quantity_as_plan_drawing_BLT000250_20260731132914_BLT000250 BOQ APD TAWANGSARI RW 04 BLITAR.xlsx | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/rfs?cluster_code=BLT000250&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8305&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:09 | ATP CLUSTER - RFS | CLUSTER | RFS | BLT000250 | TAWANGSARI RW 04 BLITAR | WO/BLITAR/2026/INST/10/8305 | Technology Karya Mandiri | core_management | Core Management | ON REVIEW | 1 | 2026-08-19 12:40 | [5 empty] | core_management_BLT000250_20260819123946_BLT000250 HPDB PRE ABD TAWANGSARI RW 04 BLITAR.xlsx | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/rfs?cluster_code=BLT000250&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8305&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:09 | ATP CLUSTER - RFS | CLUSTER | RFS | BLT000250 | TAWANGSARI RW 04 BLITAR | WO/BLITAR/2026/INST/10/8305 | Technology Karya Mandiri | justifikasi_berita_acara_opname | Justifikasi Berita Acara Opname | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/rfs?cluster_code=BLT000250&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8305&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:09 | ATP CLUSTER - RFS | CLUSTER | RFS | BLT000250 | TAWANGSARI RW 04 BLITAR | WO/BLITAR/2026/INST/10/8305 | Technology Karya Mandiri | project_opname | Project Opname | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/rfs?cluster_code=BLT000250&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8305&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:09 | ATP CLUSTER - RFS | CLUSTER | RFS | BLT000250 | TAWANGSARI RW 04 BLITAR | WO/BLITAR/2026/INST/10/8305 | Technology Karya Mandiri | subfeeder_project_opname | Project Opname Subfeeder | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/rfs?cluster_code=BLT000250&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8305&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:10 | PROJECT OPNAME - CLUSTER | CLUSTER | PROJECT OPNAME | BLT000250 | TAWANGSARI RW 04 BLITAR | WO/BLITAR/2026/INST/10/8305 | Technology Karya Mandiri | build_of_quantity_as_built_drawing | ABD BoQ Cluster | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/material/cluster/project-opname/review?cluster_code=BLT000250&work_order_number=WO/ALL/2026/DOCU/16/79674&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:10 | PROJECT OPNAME - CLUSTER | CLUSTER | PROJECT OPNAME | BLT000250 | TAWANGSARI RW 04 BLITAR | WO/BLITAR/2026/INST/10/8305 | Technology Karya Mandiri | as_built_drawing_dwg | ABD Cluster DWG | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/material/cluster/project-opname/review?cluster_code=BLT000250&work_order_number=WO/ALL/2026/DOCU/16/79674&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:10 | PROJECT OPNAME - CLUSTER | CLUSTER | PROJECT OPNAME | BLT000250 | TAWANGSARI RW 04 BLITAR | WO/BLITAR/2026/INST/10/8305 | Technology Karya Mandiri | as_built_drawing_kmz | ABD Cluster KMZ | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/material/cluster/project-opname/review?cluster_code=BLT000250&work_order_number=WO/ALL/2026/DOCU/16/79674&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:10 | PROJECT OPNAME - CLUSTER | CLUSTER | PROJECT OPNAME | BLT000250 | TAWANGSARI RW 04 BLITAR | WO/BLITAR/2026/INST/10/8305 | Technology Karya Mandiri | build_of_quantity_as_plan_drawing | BoQ APD | APPROVED | 1 | 2026-07-31 13:29 | ifam.famula |  |  |  |  | build_of_quantity_as_plan_drawing_BLT000250_20260731132914_BLT000250 BOQ APD TAWANGSARI RW 04 BLITAR.xlsx | https://astri.morarepublic.co.id/material/cluster/project-opname/review?cluster_code=BLT000250&work_order_number=WO/ALL/2026/DOCU/16/79674&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:10 | PROJECT OPNAME - CLUSTER | CLUSTER | PROJECT OPNAME | BLT000250 | TAWANGSARI RW 04 BLITAR | WO/BLITAR/2026/INST/10/8305 | Technology Karya Mandiri | build_of_quantity_project_opname | BOQ Project Opname | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/material/cluster/project-opname/review?cluster_code=BLT000250&work_order_number=WO/ALL/2026/DOCU/16/79674&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:10 | PROJECT OPNAME - CLUSTER | CLUSTER | PROJECT OPNAME | BLT000250 | TAWANGSARI RW 04 BLITAR | WO/BLITAR/2026/INST/10/8305 | Technology Karya Mandiri | justifikasi_berita_acara_opname | Justifikasi Berita Acara Opname | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/material/cluster/project-opname/review?cluster_code=BLT000250&work_order_number=WO/ALL/2026/DOCU/16/79674&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:10 | PROJECT OPNAME - CLUSTER | CLUSTER | PROJECT OPNAME | BLT000250 | TAWANGSARI RW 04 BLITAR | WO/BLITAR/2026/INST/10/8305 | Technology Karya Mandiri | opm_otdr_acceptance_test | OPM / OTDR ATP | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/material/cluster/project-opname/review?cluster_code=BLT000250&work_order_number=WO/ALL/2026/DOCU/16/79674&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:10 | PROJECT OPNAME - CLUSTER | CLUSTER | PROJECT OPNAME | BLT000250 | TAWANGSARI RW 04 BLITAR | WO/BLITAR/2026/INST/10/8305 | Technology Karya Mandiri | project_opname | Project Opname | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/material/cluster/project-opname/review?cluster_code=BLT000250&work_order_number=WO/ALL/2026/DOCU/16/79674&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:11 | ATP SUBFEEDER - CW ATP | SUBFEEDER | CW ATP | BLT000250 | TAWANGSARI RW 04 BLITAR | WO/BLITAR/2026/INST/10/8305 | Technology Karya Mandiri | as_plan_drawing_core_management_subfeeder | APD Core Management Subfeeder | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/subfeeder/list/by-invoice-phase/cw-atp?cluster_code=BLT000250&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8305&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:11 | ATP SUBFEEDER - CW ATP | SUBFEEDER | CW ATP | BLT000250 | TAWANGSARI RW 04 BLITAR | WO/BLITAR/2026/INST/10/8305 | Technology Karya Mandiri | as_plan_drawing_subfeeder_dwg | APD Subfeeder dwg | APPROVED | 1 | 2026-07-30 16:11 | ifam.famula |  |  |  |  | as_plan_drawing_subfeeder_dwg_BLT000250_20260730161059_BLT000250 DWG APD SF TAWANGSARI RW 04 BLITAR.dwg | https://astri.morarepublic.co.id/rfs-document/subfeeder/list/by-invoice-phase/cw-atp?cluster_code=BLT000250&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8305&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:11 | ATP SUBFEEDER - CW ATP | SUBFEEDER | CW ATP | BLT000250 | TAWANGSARI RW 04 BLITAR | WO/BLITAR/2026/INST/10/8305 | Technology Karya Mandiri | as_plan_drawing_subfeeder_kmz | APD Subfeeder kmz | APPROVED | 2 | 2026-08-03 16:04 | ifam.famula |  |  |  |  | as_plan_drawing_subfeeder_kmz_BLT000250_20260803160424_BLT000250 KMZ APD SF TAWANGSARI RW 04 BLITAR.KMZ | https://astri.morarepublic.co.id/rfs-document/subfeeder/list/by-invoice-phase/cw-atp?cluster_code=BLT000250&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8305&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:11 | ATP SUBFEEDER - CW ATP | SUBFEEDER | CW ATP | BLT000250 | TAWANGSARI RW 04 BLITAR | WO/BLITAR/2026/INST/10/8305 | Technology Karya Mandiri | permit_subfeeder | BA Permit Subfeeder | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/subfeeder/list/by-invoice-phase/cw-atp?cluster_code=BLT000250&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8305&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:11 | ATP SUBFEEDER - CW ATP | SUBFEEDER | CW ATP | BLT000250 | TAWANGSARI RW 04 BLITAR | WO/BLITAR/2026/INST/10/8305 | Technology Karya Mandiri | subfeeder_civil_work_acceptance_test | CW ATP Subfeeder | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/subfeeder/list/by-invoice-phase/cw-atp?cluster_code=BLT000250&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8305&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:11 | ATP SUBFEEDER - CW ATP | SUBFEEDER | CW ATP | BLT000250 | TAWANGSARI RW 04 BLITAR | WO/BLITAR/2026/INST/10/8305 | Technology Karya Mandiri | subfeeder_redline | Redline Subfeeder | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/subfeeder/list/by-invoice-phase/cw-atp?cluster_code=BLT000250&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8305&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:11 | ATP SUBFEEDER - FULL OPM | SUBFEEDER | FULL OPM | BLT000250 | TAWANGSARI RW 04 BLITAR | WO/BLITAR/2026/INST/10/8305 | Technology Karya Mandiri | subfeeder_opm_otdr_acceptance_test | OPM / OTDR Subfeeder | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/subfeeder/list/by-invoice-phase/full-opm?cluster_code=BLT000250&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8305&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:11 | ATP SUBFEEDER - RFS | SUBFEEDER | RFS | BLT000250 | TAWANGSARI RW 04 BLITAR | WO/BLITAR/2026/INST/10/8305 | Technology Karya Mandiri | as_built_drawing_core_management_subfeeder | ABD Core Management Subfeeder | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/subfeeder/list/by-invoice-phase/rfs?cluster_code=BLT000250&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8305&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:11 | ATP SUBFEEDER - RFS | SUBFEEDER | RFS | BLT000250 | TAWANGSARI RW 04 BLITAR | WO/BLITAR/2026/INST/10/8305 | Technology Karya Mandiri | as_build_drawing_subfeeder_dwg | ABD Subfeeder dwg | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/subfeeder/list/by-invoice-phase/rfs?cluster_code=BLT000250&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8305&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:11 | ATP SUBFEEDER - RFS | SUBFEEDER | RFS | BLT000250 | TAWANGSARI RW 04 BLITAR | WO/BLITAR/2026/INST/10/8305 | Technology Karya Mandiri | as_built_drawing_subfeeder_kmz | ABD Subfeeder kmz | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/subfeeder/list/by-invoice-phase/rfs?cluster_code=BLT000250&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8305&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:11 | ATP SUBFEEDER - RFS | SUBFEEDER | RFS | BLT000250 | TAWANGSARI RW 04 BLITAR | WO/BLITAR/2026/INST/10/8305 | Technology Karya Mandiri | build_of_quantity_subfeeder_as_built_drawing | BoQ Subfeeder ABD | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/subfeeder/list/by-invoice-phase/rfs?cluster_code=BLT000250&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8305&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:11 | ATP SUBFEEDER - RFS | SUBFEEDER | RFS | BLT000250 | TAWANGSARI RW 04 BLITAR | WO/BLITAR/2026/INST/10/8305 | Technology Karya Mandiri | build_of_quantity_subfeeder_as_plan_drawing | BoQ Subfeeder APD | APPROVED | 1 | 2026-07-30 16:11 | ifam.famula |  |  |  |  | build_of_quantity_subfeeder_as_plan_drawing_BLT000250_20260730161100_BLT000250 BOQ APD SF TAWANGSARI RW 04 BLITAR.xlsx | https://astri.morarepublic.co.id/rfs-document/subfeeder/list/by-invoice-phase/rfs?cluster_code=BLT000250&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8305&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:11 | ATP SUBFEEDER - RFS | SUBFEEDER | RFS | BLT000250 | TAWANGSARI RW 04 BLITAR | WO/BLITAR/2026/INST/10/8305 | Technology Karya Mandiri | justifikasi_berita_acara_opname | Justifikasi Berita Acara Opname | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/subfeeder/list/by-invoice-phase/rfs?cluster_code=BLT000250&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8305&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 17:11 | ATP SUBFEEDER - RFS | SUBFEEDER | RFS | BLT000250 | TAWANGSARI RW 04 BLITAR | WO/BLITAR/2026/INST/10/8305 | Technology Karya Mandiri | subfeeder_project_opname | Project Opname Subfeeder | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/subfeeder/list/by-invoice-phase/rfs?cluster_code=BLT000250&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8305&vendor_label=Technology%20Karya%20Mandiri