## Astri_Status
scraped_at | route | scope | phase | cluster_code | clean_list_name | work_order_number | vendor_label | astri_type | astri_label | derived_status | file_count | upload_date | verified_by | verified_at | revision_by | revision_at | revision_remark | filename | detail_url
2026-08-19 16:49 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | as_plan_drawing_dwg | APD DWG Cluster | APPROVED | 1 | 2026-08-04 11:43 | ifam.famula |  |  |  |  | as_plan_drawing_dwg_BLT000695_20260804114328_BLT000695 DWG APD BENCE RW 06 BLITAR.dwg | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 16:49 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | as_plan_drawing_kmz | APD KMZ Cluster | APPROVED | 3 | 2026-08-10 11:48 | ifam.famula |  |  |  |  | as_plan_drawing_kmz_BLT000695_20260810114823_BLT000695 KMZ APD BENCE RW 06 BLITAR.kmz | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 16:49 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | as_plan_drawing_subfeeder_kmz | APD Subfeeder kmz | APPROVED | 2 | 2026-08-10 12:30 | ifam.famula |  |  |  |  | as_plan_drawing_subfeeder_kmz_BLT000695_20260810122940_BLT000695 KMZ SF APD BENCE RW 06 BLITAR.KMZ | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 16:49 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | permit_subfeeder | BA Permit Subfeeder | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 16:49 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | permit_cluster_aggreement | Berita Acara Kesepakatan | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 16:49 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | permit_open | Berita Acara Open | ON REVIEW | 1 | 2026-08-10 10:34 | [5 empty] | permit_open_BLT000695_20260810103330_BA_OPEN_BENCE_RW_06_BLITAR.pdf | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 16:49 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | donation_approval | Cluster Approval Proposal | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 16:49 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | civil_work_acceptance_test | CW ATP | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 16:49 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | subfeeder_civil_work_acceptance_test | CW ATP Subfeeder | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 16:49 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | cluster_survey_form | Form Cluster Survey | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 16:49 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | permit_vip_form | Form Free Layanan | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 16:49 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | homepass_database | Homepass Database | APPROVED | 1 | 2026-08-04 11:43 | ifam.famula |  |  |  |  | homepass_database_BLT000695_20260804114328_BLT000695 HPDB APD BENCE RW 06 BLITAR.xlsx | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 16:49 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | rough_design_layout | Layout SnD Kasar | ON REVIEW | 1 | 2026-08-10 10:34 | [5 empty] | rough_design_layout_BLT000695_20260810103331_Hasil Valsal Cluster BENCE RW 06 BLITAR.pdf | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 16:49 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | sales_validation_layout | Layout Validasi Sales | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 16:49 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | ptsp | PTSP | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 16:49 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | redline | Redline | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 16:49 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | subfeeder_redline | Redline Subfeeder | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 16:49 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | rekomtek | Rekomtek | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 16:49 | ATP CLUSTER - CW ATP | CLUSTER | CW ATP | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | tssr | TSSR | APPROVED | 1 | 2026-08-04 11:44 | ifam.famula |  |  |  |  | tssr_BLT000695_20260804114330_BLT000695 TSSR BENCE RW 06 BLITAR.pdf | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/cw-atp?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 16:50 | ATP CLUSTER - FULL OPM | CLUSTER | FULL OPM | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | opm_otdr_acceptance_test | OPM / OTDR ATP | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/full-opm?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 16:50 | ATP CLUSTER - RFS | CLUSTER | RFS | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | build_of_quantity_as_built_drawing | ABD BoQ Cluster | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/rfs?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 16:50 | ATP CLUSTER - RFS | CLUSTER | RFS | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | as_built_drawing_dwg | ABD Cluster DWG | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/rfs?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 16:50 | ATP CLUSTER - RFS | CLUSTER | RFS | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | as_built_drawing_kmz | ABD Cluster KMZ | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/rfs?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 16:50 | ATP CLUSTER - RFS | CLUSTER | RFS | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | build_of_quantity_as_plan_drawing | BoQ APD | APPROVED | 1 | 2026-08-04 11:44 | ifam.famula |  |  |  |  | build_of_quantity_as_plan_drawing_BLT000695_20260804114329_BLT000695 BOQ APD BENCE RW 06 BLITAR.xlsx | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/rfs?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 16:50 | ATP CLUSTER - RFS | CLUSTER | RFS | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | core_management | Core Management | ON REVIEW | 1 | 2026-08-19 15:54 | [5 empty] | core_management_BLT000695_20260819155348_BLT000695 HPDB PRE ABD BENCE RW 06 BLITAR.xlsx | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/rfs?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 16:50 | ATP CLUSTER - RFS | CLUSTER | RFS | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | justifikasi_berita_acara_opname | Justifikasi Berita Acara Opname | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/rfs?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 16:50 | ATP CLUSTER - RFS | CLUSTER | RFS | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | project_opname | Project Opname | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/rfs?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 16:50 | ATP CLUSTER - RFS | CLUSTER | RFS | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | subfeeder_project_opname | Project Opname Subfeeder | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/list/by-invoice-phase/rfs?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 16:50 | PROJECT OPNAME - CLUSTER | CLUSTER | PROJECT OPNAME | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | build_of_quantity_as_built_drawing | ABD BoQ Cluster | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/material/cluster/project-opname/review?cluster_code=BLT000695&work_order_number=WO/ALL/2026/DOCU/16/80008&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 16:50 | PROJECT OPNAME - CLUSTER | CLUSTER | PROJECT OPNAME | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | as_built_drawing_dwg | ABD Cluster DWG | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/material/cluster/project-opname/review?cluster_code=BLT000695&work_order_number=WO/ALL/2026/DOCU/16/80008&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 16:50 | PROJECT OPNAME - CLUSTER | CLUSTER | PROJECT OPNAME | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | as_built_drawing_kmz | ABD Cluster KMZ | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/material/cluster/project-opname/review?cluster_code=BLT000695&work_order_number=WO/ALL/2026/DOCU/16/80008&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 16:50 | PROJECT OPNAME - CLUSTER | CLUSTER | PROJECT OPNAME | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | build_of_quantity_as_plan_drawing | BoQ APD | APPROVED | 1 | 2026-08-04 11:44 | ifam.famula |  |  |  |  | build_of_quantity_as_plan_drawing_BLT000695_20260804114329_BLT000695 BOQ APD BENCE RW 06 BLITAR.xlsx | https://astri.morarepublic.co.id/material/cluster/project-opname/review?cluster_code=BLT000695&work_order_number=WO/ALL/2026/DOCU/16/80008&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 16:50 | PROJECT OPNAME - CLUSTER | CLUSTER | PROJECT OPNAME | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | build_of_quantity_project_opname | BOQ Project Opname | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/material/cluster/project-opname/review?cluster_code=BLT000695&work_order_number=WO/ALL/2026/DOCU/16/80008&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 16:50 | PROJECT OPNAME - CLUSTER | CLUSTER | PROJECT OPNAME | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | justifikasi_berita_acara_opname | Justifikasi Berita Acara Opname | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/material/cluster/project-opname/review?cluster_code=BLT000695&work_order_number=WO/ALL/2026/DOCU/16/80008&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 16:50 | PROJECT OPNAME - CLUSTER | CLUSTER | PROJECT OPNAME | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | opm_otdr_acceptance_test | OPM / OTDR ATP | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/material/cluster/project-opname/review?cluster_code=BLT000695&work_order_number=WO/ALL/2026/DOCU/16/80008&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 16:50 | PROJECT OPNAME - CLUSTER | CLUSTER | PROJECT OPNAME | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | project_opname | Project Opname | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/material/cluster/project-opname/review?cluster_code=BLT000695&work_order_number=WO/ALL/2026/DOCU/16/80008&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 16:50 | ATP SUBFEEDER - CW ATP | SUBFEEDER | CW ATP | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | as_plan_drawing_core_management_subfeeder | APD Core Management Subfeeder | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/subfeeder/list/by-invoice-phase/cw-atp?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 16:50 | ATP SUBFEEDER - CW ATP | SUBFEEDER | CW ATP | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | as_plan_drawing_subfeeder_dwg | APD Subfeeder dwg | APPROVED | 1 | 2026-08-04 12:06 | ifam.famula |  |  |  |  | as_plan_drawing_subfeeder_dwg_BLT000695_20260804120542_BLT000695 DWG SF APD BENCE RW 06 BLITAR.dwg | https://astri.morarepublic.co.id/rfs-document/subfeeder/list/by-invoice-phase/cw-atp?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 16:50 | ATP SUBFEEDER - CW ATP | SUBFEEDER | CW ATP | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | as_plan_drawing_subfeeder_kmz | APD Subfeeder kmz | APPROVED | 2 | 2026-08-10 12:30 | ifam.famula |  |  |  |  | as_plan_drawing_subfeeder_kmz_BLT000695_20260810122940_BLT000695 KMZ SF APD BENCE RW 06 BLITAR.KMZ | https://astri.morarepublic.co.id/rfs-document/subfeeder/list/by-invoice-phase/cw-atp?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 16:50 | ATP SUBFEEDER - CW ATP | SUBFEEDER | CW ATP | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | permit_subfeeder | BA Permit Subfeeder | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/subfeeder/list/by-invoice-phase/cw-atp?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 16:50 | ATP SUBFEEDER - CW ATP | SUBFEEDER | CW ATP | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | subfeeder_civil_work_acceptance_test | CW ATP Subfeeder | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/subfeeder/list/by-invoice-phase/cw-atp?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 16:50 | ATP SUBFEEDER - CW ATP | SUBFEEDER | CW ATP | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | subfeeder_redline | Redline Subfeeder | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/subfeeder/list/by-invoice-phase/cw-atp?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 16:51 | ATP SUBFEEDER - FULL OPM | SUBFEEDER | FULL OPM | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | subfeeder_opm_otdr_acceptance_test | OPM / OTDR Subfeeder | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/subfeeder/list/by-invoice-phase/full-opm?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 16:51 | ATP SUBFEEDER - RFS | SUBFEEDER | RFS | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | as_built_drawing_core_management_subfeeder | ABD Core Management Subfeeder | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/subfeeder/list/by-invoice-phase/rfs?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 16:51 | ATP SUBFEEDER - RFS | SUBFEEDER | RFS | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | as_build_drawing_subfeeder_dwg | ABD Subfeeder dwg | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/subfeeder/list/by-invoice-phase/rfs?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 16:51 | ATP SUBFEEDER - RFS | SUBFEEDER | RFS | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | as_built_drawing_subfeeder_kmz | ABD Subfeeder kmz | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/subfeeder/list/by-invoice-phase/rfs?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 16:51 | ATP SUBFEEDER - RFS | SUBFEEDER | RFS | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | build_of_quantity_subfeeder_as_built_drawing | BoQ Subfeeder ABD | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/subfeeder/list/by-invoice-phase/rfs?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 16:51 | ATP SUBFEEDER - RFS | SUBFEEDER | RFS | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | build_of_quantity_subfeeder_as_plan_drawing | BoQ Subfeeder APD | APPROVED | 1 | 2026-08-04 12:06 | ifam.famula |  |  |  |  | build_of_quantity_subfeeder_as_plan_drawing_BLT000695_20260804120543_BLT000695 BOQ SF APD BENCE RW 06 BLITAR.xlsx | https://astri.morarepublic.co.id/rfs-document/subfeeder/list/by-invoice-phase/rfs?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 16:51 | ATP SUBFEEDER - RFS | SUBFEEDER | RFS | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | justifikasi_berita_acara_opname | Justifikasi Berita Acara Opname | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/subfeeder/list/by-invoice-phase/rfs?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri
2026-08-19 16:51 | ATP SUBFEEDER - RFS | SUBFEEDER | RFS | BLT000695 | BENCE RW 06 BLITAR | WO/BLITAR/2026/INST/10/8309 | Technology Karya Mandiri | subfeeder_project_opname | Project Opname Subfeeder | NOT UPLOADED | 0 | [7 empty] | https://astri.morarepublic.co.id/rfs-document/subfeeder/list/by-invoice-phase/rfs?cluster_code=BLT000695&work_order_number=WO%2FBLITAR%2F2026%2FINST%2F10%2F8309&vendor_label=Technology%20Karya%20Mandiri