## TO DO LIST
MONITORING WEBSITE TKM
No | PAGE | Menu | Section | Detail | PIC | Bobot | Jam | Progress Baru | VALUE | (-) | CEK | DATE CHECK
1 | DB | Database | Input Database | DB | LUTHFI | 1 | 2 |  | 0 | 2 |  |  | R | DONE
2 | Template | Template | Template Halaman | Frontend | LUTHFI | 2 | 4 |  | 0 | 4 |  |  | S | NY
3 | Login | Login | DesignHalaman Login | Frontend | LUTHFI | 1 | 2 |  | 0 | 2
4 |  |  | Validasi Login | Backend | LUTHFI | 1 | 2 |  | 0 | 2 |  |  | 335 | HOURS PROGRESS | 100% | TOTAL EST PROGRESS
5 | Dashboard | Dashboard | Design Halaman Dashboard | Frontend | LUTHFI | 8 | 16 |  | 0 | 16 |  |  | 41.875 | DAY PROGRESS
6 |  |  | Set Actual Data | Backend | REIKY | 8 | 16 |  | 0 | 16 |  |  | 6.9792 | WEEK PROGRESS
7 | Master Area | List Area | Design Halaman List Area | Frontend | LUTHFI | 4 | 8 |  | 0 | 8 |  |  | 1.7448 | MONTH PROGRESS
8 |  |  | Set Data List Area | Backend | LUTHFI | 2 | 4 |  | 0 | 4
9 |  | Tambah Area | Design Popup Tambah Area | Frontend | LUTHFI | 1 | 2 |  | 0 | 2 |  |  | 0 | HOURS PROGRESS | 0% | TOTAL DONE PROGRESS
10 |  |  | Tambah Area To DB | Backend | LUTHFI | 1 | 2 |  | 0 | 2 |  |  | 0 | DAY PROGRESS
11 |  | Edit Area | Design Popup Edit Area | Frontend | LUTHFI | 1 | 2 |  | 0 | 2 |  |  | 0 | WEEK PROGRESS
12 |  |  | Edit Area To DB | Backend | LUTHFI | 1 | 2 |  | 0 | 2 |  |  | 0 | MONTH PROGRESS
13 |  | Hapus Area | Hapus Area To DB | Backend | LUTHFI | 0.5 | 1 |  | 0 | 1
14 | Master User | List User | Design Halaman List User | Frontend | LUTHFI | 4 | 8 |  | 0 | 8 |  |  | 335 | HOURS PROGRESS | 100% | TOTAL OGP PROGRESS
15 |  |  | Set Data List User | Backend | LUTHFI | 2 | 4 |  | 0 | 4 |  |  | 41.875 | DAY PROGRESS
16 |  | Tambah User | Design Popup Tambah User | Frontend | LUTHFI | 1 | 2 |  | 0 | 2 |  |  | 6.9792 | WEEK PROGRESS
17 |  |  | Tambah User To DB | Backend | LUTHFI | 1 | 2 |  | 0 | 2 |  |  | 1.7448 | MONTH PROGRESS
18 |  | Edit User | Design Popup Edit User | Frontend | LUTHFI | 1 | 2 |  | 0 | 2
19 |  |  | Edit User To DB | Backend | LUTHFI | 1 | 2 |  | 0 | 2
20 |  | Hapus User | Hapus User To DB | Backend | LUTHFI | 0.5 | 1 |  | 0 | 1
21 | Master Bowheer | List Bowheer | Design Halaman List Bowheer | Frontend | LUTHFI | 4 | 8 |  | 0 | 8
22 |  |  | Set Data List Bowheer | Backend | LUTHFI | 2 | 4 |  | 0 | 4
23 |  | Tambah Bowheer | Design Popup Tambah Bowheer | Frontend | LUTHFI | 1 | 2 |  | 0 | 2
24 |  |  | Tambah Bowheer To DB | Backend | LUTHFI | 1 | 2 |  | 0 | 2
25 |  | Edit Bowheer | Design Popup Edit Bowheer | Frontend | LUTHFI | 1 | 2 |  | 0 | 2
26 |  |  | Edit Bowheer To DB | Backend | LUTHFI | 1 | 2 |  | 0 | 2
27 |  | Hapus Bowheer | Hapus Bowheer To DB | Backend | LUTHFI | 0.5 | 1 |  | 0 | 1
28 | Master Lokasi Gudang | List Lokasi Gudang | Design Halaman List Lokasi Gudang | Frontend | LUTHFI | 4 | 8 |  | 0 | 8
29 |  |  | Set Data List Lokasi Gudang | Backend | LUTHFI | 2 | 4 |  | 0 | 4
30 |  | Tambah Lokasi Gudang | Design Popup Tambah Lokasi Gudang | Frontend | LUTHFI | 1 | 2 |  | 0 | 2
31 |  |  | Tambah Lokasi Gudang To DB | Backend | LUTHFI | 1 | 2 |  | 0 | 2
32 |  | Edit Lokasi Gudang | Design Popup Edit Lokasi Gudang | Frontend | LUTHFI | 1 | 2 |  | 0 | 2
33 |  |  | Edit Lokasi Gudang To DB | Backend | LUTHFI | 1 | 2 |  | 0 | 2
34 |  | Hapus Lokasi Gudang | Hapus Lokasi Gudang To DB | Backend | LUTHFI | 0.5 | 1 |  | 0 | 1
35 | Master Kode Item | List Kode Item | Design Halaman List Kode Item | Frontend | LUTHFI | 4 | 8 |  | 0 | 8
36 |  |  | Set Data List Kode Item | Backend | LUTHFI | 2 | 4 |  | 0 | 4
37 |  | Tambah Kode Item | Design Popup Tambah Kode Item | Frontend | LUTHFI | 1 | 2 |  | 0 | 2
38 |  |  | Tambah Kode Item To DB | Backend | LUTHFI | 1 | 2 |  | 0 | 2
39 |  | Edit Kode Item | Design Popup Edit Kode Item | Frontend | LUTHFI | 1 | 2 |  | 0 | 2
40 |  |  | Edit Kode Item To DB | Backend | LUTHFI | 1 | 2 |  | 0 | 2
41 |  | Hapus Kode Item | Hapus Kode Item To DB | Backend | LUTHFI | 0.5 | 1 |  | 0 | 1
42 | Master Sumber Material | List Sumber Material | Design Halaman List Sumber Material | Frontend | LUTHFI | 4 | 8 |  | 0 | 8
43 |  |  | Set Data List Sumber Material | Backend | LUTHFI | 2 | 4 |  | 0 | 4
44 |  | Tambah Sumber Material | Design Popup Tambah Sumber Material | Frontend | LUTHFI | 1 | 2 |  | 0 | 2
45 |  |  | Tambah Sumber Material To DB | Backend | LUTHFI | 1 | 2 |  | 0 | 2
46 |  | Edit Sumber Material | Design Popup Edit Sumber Material | Frontend | LUTHFI | 1 | 2 |  | 0 | 2
47 |  |  | Edit Sumber Material To DB | Backend | LUTHFI | 1 | 2 |  | 0 | 2
48 |  | Hapus Sumber Material | Hapus Sumber Material To DB | Backend | LUTHFI | 0.5 | 1 |  | 0 | 1
49 | Dashboard Logistik | Dashboard | Design Halaman Dashboard | Frontend | LUTHFI | 2 | 4 |  | 0 | 4
50 |  |  | Set Data List Dashboard | Backend | LUTHFI | 2 | 4 |  | 0 | 4
51 |  |  | Filter Data | Backend | LUTHFI | 1 | 2 |  | 0 | 2
52 |  | Tambah Data Masuk | Design Popup Tambah Data Dashboard | Frontend | LUTHFI | 1 | 2 |  | 0 | 2
53 |  |  | Tambah Data Dashboard | Backend | LUTHFI | 2 | 4 |  | 0 | 4
|  |  | Upload Foto Surat Jalan | Frontend |  | 2 | 4 |  | 0 | 4
|  | Tambah Data Keluar | Design Popup Tambah Data Dashboard | Frontend | LUTHFI | 1 | 2 |  | 0 | 2
|  |  | Tambah Data Dashboard | Backend | LUTHFI | 2 | 4 |  | 0 | 4
|  |  | Upload Foto Surat Jalan | Frontend |  | 2 | 4 |  | 0 | 4
54 | Master Pabrik | List Pabrik | Design Halaman List Pabrik | Frontend | LUTHFI | 1 | 2 |  | 0 | 2
55 |  |  | Set Data List Pabrik | Backend | LUTHFI | 1 | 2 |  | 0 | 2
56 |  | Tambah Pabrik | Design Popup List Pabrik | Frontend | LUTHFI | 1 | 2 |  | 0 | 2
57 |  |  | Tambah Pabrik To DB | Backend | LUTHFI | 1 | 2 |  | 0 | 2
58 |  | Edit Pabrik | Design Popup Edit Pabrik | Frontend | LUTHFI | 1 | 2 |  | 0 | 2
59 |  |  | Edit Pabrik To DB | Backend | LUTHFI | 1 | 2 |  | 0 | 2
60 |  | Hapus Pabrik | Hapus Pabrik To DB | Backend | LUTHFI | 1 | 2 |  | 0 | 2
61 | PO Pabrik | Dashboard | Design Halaman PO Pabrik | Frontend | LUTHFI | 1 | 2 |  | 0 | 2
62 |  |  | Set Data List PO Pabrik | Backend | LUTHFI | 1 | 2 |  | 0 | 2
63 |  | Tambah PO Pabrik | Design Popup Tambah PO Pabrik | Frontend | LUTHFI | 1 | 2 |  | 0 | 2
64 |  |  | Tambah PO Pabrik To DB | Backend | LUTHFI | 1 | 2 |  | 0 | 2
65 |  | Edit PO Pabrik | Design Popup Edit PO Pabrik | Frontend | LUTHFI | 1 | 2 |  | 0 | 2
66 |  |  | Edit PO Pabrik To DB | Backend | LUTHFI | 1 | 2 |  | 0 | 2
67 |  | Edit Status PO Pabrik | Design Popup Edit Status PO Pabrik | Frontend | LUTHFI | 1 | 2 |  | 0 | 2
68 |  |  | Edit Status PO Pabrik | Backend | LUTHFI | 1 | 2 |  | 0 | 2
69 |  | Hapus PO Pabrik | Hapus PO Pabrik To DB | Backend | LUTHFI | 1 | 2 |  | 0 | 2
70 | List Project Fiberstar | Dashboard | Design Halaman Dashboard | Frontend | LUTHFI | 4 | 8 |  | 0 | 8
71 |  |  | Set Data List Dashboard | Backend | LUTHFI | 2 | 4 |  | 0 | 4
72 |  |  | Filter Data | Backend | LUTHFI | 12 | 24 |  | 0 | 24
73 |  |  | Set Data Stagging Regional | Backend | LUTHFI | 2 | 4 |  | 0 | 4
74 |  |  | Set Data Stagging Area | Backend | LUTHFI | 2 | 4 |  | 0 | 4
75 |  |  | Chart Dashboard | Frontend | LUTHFI | 8 | 16 |  | 0 | 16
76 |  |  | Persentase Nilai PO | Frontend | LUTHFI | 1 | 2 |  | 0 | 2
77 |  |  | Filter Tanggal Untuk Chart dan Table | Frontend | LUTHFI | 2 | 4 |  | 0 | 4
78 |  |  | Download Report Excel | Frontend | LUTHFI | 2 | 4 |  | 0 | 4
79 |  |  | Download Report PDF | Frontend | LUTHFI | 2 | 4 |  | 0 | 4
80 |  |  | Tambah Data | Frontend | LUTHFI | 1 | 2 |  | 0 | 2
81 |  |  | Tambah Data to DB | Backend | LUTHFI | 1 | 2 |  | 0 | 2
82 | Detail List Project Fiberstar | PO & Invoice | List Data PO & Invoice | Frontend | LUTHFI | 1 | 2 |  | 0 | 2
83 |  |  | Set Data PO & Invoice | Backend | LUTHFI | 1 | 2 |  | 0 | 2
84 |  |  | Dashboard PO & Invoice | Frontend | LUTHFI | 0.5 | 1 |  | 0 | 1
85 |  | Implementasi | List Data Implementasi | Frontend | LUTHFI | 1 | 2 |  | 0 | 2
86 |  |  | Set Data Implementasi | Backend | LUTHFI | 1 | 2 |  | 0 | 2
87 |  |  | Popup Tambah BOQ | Frontend | LUTHFI | 0.5 | 1 |  | 0 | 1
88 |  |  | Tambah BOQ To DB | Backend | LUTHFI | 0.5 | 1 |  | 0 | 1
89 |  |  | Popup Tambah Implementasi | Frontend | LUTHFI | 0.5 | 1 |  | 0 | 1
90 |  |  | Tambah Implementasi To DB | Backend | LUTHFI | 0.5 | 1 |  | 0 | 1
91 |  | Checklist Dokument | List Data Checklist Dokument | Frontend | LUTHFI | 1 | 2 |  | 0 | 2
92 |  |  | Upload Dokument | Frontend | LUTHFI | 1 | 2 |  | 0 | 2
93 |  |  | Lihat Dokument | Frontend | LUTHFI | 1 | 2 |  | 0 | 2
94 |  |  | Status Approval | Frontend | LUTHFI | 4 | 8 |  | 0 | 8
[7 empty] | 0 |  | 0 | 0
[7 empty] | 335 |  | 0 | 335 |  | JAM
[7 empty] | 41.875 |  | 0 | 41.875 |  | HARI
[7 empty] | 5.9821 |  | 0 | 5.9821 |  | WEEK

## Sheet2
table 1
nomor_po | jumlah_pesanan
11111 | 5000
table 2
nomor_po | jumlah_pengiriman
11111 | 3000
11111 | 1000
hasil
nomor_po | jumlah_pesanan | jumlah_pengiriman
11111 | 5000
11111 |  | 3000
11111 |  | 1000